## Coversheet
REASON GROUP ENGAGEMENT JOB PLAN (template updated 25 AUG 2025) |  | Summary of Requirement
CLIENT INFORMATION |  | The Attorney-General's Department (the department) is seeking a 12-month contract to supply, software licensing and professional services required to build a Case Management System (CMS). AGD requires a quote for both professional services to build and the software licenses required to deliver the solution (noting: unit pricing is preferred for licenses). The resulting contract will include the ability to purchase additional software licensing and additional professional services relevant to the solution as required. Date expected to place order: Monday, 03 November 2025. Expected contract duration: 12 months. Extension term: 12 months, Number of extensions: 2
Client name | AGD - Attorney-General's Department
Client sponsor (buyer)
Client sponsor email
Client contact phone/mobile number
End client (if different to above)
Work location | Canberra
ENGAGEMENT INFORMATION |  | Delivery Assumptions
Engagement Code |  | Hadas: I had a chat with Andy, the most important for this customer is to support their maturity, OCM, how to run a project and get it right etc. We will go with PSDS Pro Plus (Now Assist) on their existing instance. We will get the Servicenow response early next week. We also need to mention how we will work with the managed service provider (he doesn't know who it is yet). He also hasn't heard from Novabridge or Xmplify so maybe they aren't in.
Engagement name | Case Management System (CMS) Licences, Build and Development – Commonwealth Parole Board
Account Manager (pre-populated from Time Plan) | Aleksandar Vranesevic
Engagement Manager (pre-populated from Time Plan) | Hadas Yehezkel
Timesheets requirement | Signed I-Time
Start date (pre-populated from Time Plan) | 2026-02-09
End date | 2026-11-02
FINANCIAL & ACCOUNT INFORMATION |  | Pricing Assumptions
PO/WO Number |  | ServiceNow pricing
PO/WO Amount (ex GST)
Project Budget Amount (ex GST) in iTimes
Variance (Project Budget to PO ex GST) | 0
Variance (Project budget to total task budget ex GST) | 0
Accounts Contact
Accounts Email Address
Invoice method
Invoice Instructions (T&M/monthly; Milestones, approvals)
SYSTEM SETUP REQUIREMENT |  | Identified Risks
MS Teams DEL channel & Planner required | Yes
-> If using existing (insert engagement code)
Legend: | TBC by CAS
TBC by CSD
TBC by OPS

## Pricing
[17 empty] | Category | Market Rates - Solutions implementation services
By Milestone/Workstream | [8 empty] | By Deliverable | [7 empty] | By Person
Milestone | Start Date | End Date | Week Number | $ ex GST | $ GST | $ inc GST | Discount | Margin | Deliverable | Start Date | End Date | $ ex GST | GST | $ inc GST | Discount | Margin | Resource | Position | Offered Hourly Rate ($ ex-GST) | Offered Hourly Rate ($ inc-GST) | Start Date | End Date | Chargeable $ ex GST | Chargeable $ inc GST | Discount % | Margin % | Forecasted Hours | Forecasted Days | Re-apportioned Hours (distribute contingency) | Re-apportioned Days (distribute contingency) | % Re-allocation of contingency | Re-allocated $ ex GST
M1 - Discovery Completion | 2026-02-09 | 2026-03-06 | 4 | 28773.2 | 2877.32 | 31650.52 | 41.38% | -0.6744% | 1.1 Detailed requirements, business process mapping | 2026-02-09 | 2026-03-06 | 28773.2 | 2877.32 | 31650.52 | 41.38% | -0.6744% | Anil Kinagi | Level 4 - Project Manager | 207.4 | 228.14 | 2026-02-09 | 2026-07-17 | 146839.2 | 161523.12 | 32% | -18.13% | 708 | 88.5
M2 - Sprint 1 and 2 completion | 2026-02-23 | 2026-03-27 | 7 | 166496.4 | 16649.64 | 183146.04 | 41.92% | -4.517% | 1.3 Detailed delivery plan, RACI of build/delivery meeting AGD Operating Model requirements |  |  | 0 | 0 | 0 |  |  | Bradley Burge | Level 4 - Lead ServiceNow Developer | 207.4 | 228.14 | 2026-02-23 | 2026-07-17 | 155428 | 170970.8 | 37.71% | 20.51% | 820 | 102.5 | 820 | 102.5 | 0% | 170068
M3 - Sprint 3 and 4 completion | 2026-03-30 | 2026-04-24 | 11 | 202558.44 | 20255.844 | 222814.284 | 37.9% | 3.404% | 1.4 Acceptance certificate |  |  | 0 | 0 | 0 |  |  | Contingency | - | 1438.66 | 1582.526 | 2026-02-16 | 2026-04-24 | 17574.04 | 19331.444 |  | 100% | 3 | 0.375 | 3 | 0.375 | 0% | 4315.98
M4 - Sprint 5 and 6 completion | 2026-04-27 | 2026-05-22 | 15 | 212800 | 21280 | 234080 | 43.1% | -6.162% | 2.1 Project management and compliance documentation | 2026-03-02 | 2026-07-17 | 227755.2 | 22775.52 | 250530.72 | 34.37% | 0.9112% | Contractor-Tester-Manager | Level 3 - Senior Tester | 151.9 | 167.09 | 2026-04-13 | 2026-06-19 | 60760 | 66836 | 38% | -5.991% | 400 | 50 | 883.3417 | 110.4177 | 50% | 134179.6
M5 - Test Completion & Go-live | 2026-05-25 | 2026-06-19 | 19 | 112048 | 11204.8 | 123252.8 | 45.45% | -21.95% | 2.2 Build | 2026-02-23 | 2026-07-17 | 518242.04 | 51824.204 | 570066.244 | 44.56% | -8.451% | Hadas Yehezkel | Level 5 - ServiceNow Architect | 237 | 260.7 | 2026-02-09 | 2026-05-22 | 54510 | 59961 | 40% | 16.46% | 230 | 28.75 | 539.7873 | 67.4734 | 50% | 127929.6
M6 - Hypercare completion | 2026-06-22 | 2026-07-17 | 23 | 52094.4 | 5209.44 | 57303.84 | 43.12% | -8.918% |  |  |  | 0 | 0 | 0 |  |  | Kosta Walker-Laskos | Level 3 - ServiceNow Developer | 151.9 | 167.09 | 2026-03-02 | 2026-07-03 | 91140 | 100254 | 38% | 0.5925% | 600 | 75 | 600 | 75 | 0% | 91140
|  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | Lacy Pejcinovic | Level 3 - Business Analyst | 151.9 | 167.09 | 2026-02-09 | 2026-03-27 | 24304 | 26734.4 | 38% | 3.884% | 160 | 20 | 160 | 20 | 0% | 24304
|  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | Lynne Sutherland | Level 3 - Business Analyst | 151.9 | 167.09 | 2026-02-09 | 2026-05-22 | 72912 | 80203.2 | 38% | 40.75% | 480 | 60 | 480 | 60 | 0% | 72912
|  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | Mahesh Vemegal | Level 4 - Lead ServiceNow Developer | 207.4 | 228.14 | 2026-02-23 | 2026-05-22 | 95404 | 104944.4 | 32% | 17.57% | 460 | 57.5 | 460 | 57.5
|  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | Michelle Chant | Level 3 - Change Manager | 151.9 | 167.09 | 2026-02-09 | 2026-06-19 | 55899.2 | 61489.12 | 38% | 3.884% | 368 | 46 | 368 | 46
|  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  | Phani Gollamudi | Level 3 - ServiceNow Developer | 0 | 0 | 2026-02-09 | 2026-07-03 | 0 | 0 | 100% |  | 660 | 82.5
|  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | - |  |  |  |  | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | - |  |  |  |  | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | - |  |  |  |  | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | - |  |  |  |  | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | - |  |  |  |  | 0 | 0 |  |  | 0 | 0
[12 empty] | 0 | 0 | 0 | [8 empty] | 0 | 0
[12 empty] | 0 | 0 | 0 | [8 empty] | 0 | 0
[12 empty] | 0 | 0 | 0 | [8 empty] | 0 | 0
[12 empty] | 0 | 0 | 0 | [8 empty] | 0 | 0
[12 empty] | 0 | 0 | 0 | [8 empty] | 0 | 0
[12 empty] | 0 | 0 | 0 |  |  |  | - |  |  |  |  | 0 | 0 |  |  | 0 | 0
[12 empty] | 0 | 0 | 0 |  |  |  | - |  |  |  |  | 0 | 0 |  |  | 0 | 0
[18 empty] | - |  |  |  |  | 0 | 0 |  |  | 0 | 0
[12 empty] | 0 | 0 | 0 |  |  |  | - |  |  |  |  | 0 | 0 |  |  | 0 | 0
|  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 |  |  |  | - |  |  |  |  | 0 | 0 |  |  | 0 | 0
[12 empty] | 0 | 0 | 0 | [8 empty] | 0 | 0
Engagement Summary | 2026-02-09 | 2026-07-17 | 23 | 774770.44 | 77477.044 | 852247.484 | 41.78% | -4.944% | Engagement Summary | 2026-02-09 | 2026-07-17 | 774770.44 | 77477.044 | 852247.484 | 41.78% | -4.944% | Engagement Summary |  |  |  | 2026-02-09 | 2026-07-17 | 774770.44 | 852247.484 | 41.78% | -4.944% | 4889 | 611.125 | 4314.129 | 539.2661 | 100% | 624849.18
[19 empty] | 708 | 0
749.4118
12.2156
400
230
600
160
480
460
906
480
420
760
420
1140
480
4606
Formulas:
Start Date = IFERROR(INDEX('Time Plan (Single Release)'!$Y3:JN3, 1, XMATCH(TRUE, BYCOL(('Time Plan (Single Release)'!$Y6:JN64)*('Time Plan (Single Release)'!$B6:B64=[By Milestone/Workstream]), LAMBDA(_xlpm.col, SUM(_xlpm.col)>0)), 0, 1)),"")
Start Date = IFERROR(INDEX('Time Plan (Single Release)'!$Y3:JN3, 1, XMATCH(TRUE, BYCOL(('Time Plan (Single Release)'!$Y6:JN64)*('Time Plan (Single Release)'!$C6:C64=[By Deliverable]), LAMBDA(_xlpm.col, SUM(_xlpm.col)>0)), 0, 1)),"")
End Date = IFERROR(INDEX('Time Plan (Single Release)'!$Y3:JN3, 1, XMATCH(TRUE, BYCOL(('Time Plan (Single Release)'!$Y6:JN64)*('Time Plan (Single Release)'!$B6:B64=[By Milestone/Workstream]), LAMBDA(_xlpm.col, SUM(_xlpm.col)>0)), 0,-1))+4,"")
End Date = IFERROR(INDEX('Time Plan (Single Release)'!$Y3:JN3, 1, XMATCH(TRUE, BYCOL(('Time Plan (Single Release)'!$Y6:JN64)*('Time Plan (Single Release)'!$C6:C64=[By Deliverable]), LAMBDA(_xlpm.col, SUM(_xlpm.col)>0)), 0,-1))+4,"")
Week Number = IFERROR(DATEDIF('Time Plan (Single Release)'!$Y3,[End Date]+3,"d")/7,"")

## Exemplars
Forecast Date | 2025-05-19 | [21 empty] | Monday Commencing (Select)
Contract Start Date | 2025-05-20 | [8 empty] | Delivery | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80
Milestone | Deliverable | Resource | Charge Out Level | Job Role | Panel Hourly Rate $ ex-GST | Discount % | Discounted Hourly Rate $ ex GST | Panel Daily Rate $ ex-GST | Hourly Gross Cost $ | Budget Hours | Budget $ ex GST | Actual Hours as at 20-May | Charge $ ex GST | Balance $ ex GST (Budget - Charge) | Gross Cost $ ex GST | Gross Margin | Forecast hours | Forecast Days | Forecast $ ex GST | Forecast Gross Cost $ ex GST | Variance at completion ex GST | Variance at completion % | time axis 2025-05-19 to 2026-11-23
| Account Manager | Aleksandar Vranesevic | Panel | Boston Consulting Group (BCG) - Partner Rates | [18 empty] | 2025-06-02: 20%; 2025-06-09: 20%; 2025-10-06: 20%; 2025-12-22: 100%; 2025-12-29: 100%; 2026-01-26: 20%; 2026-03-09: 20%; 2026-03-30: 20%; 2026-04-06: 20%; 2026-04-20: 20%; 2026-06-01: 20%; 2026-06-08: 20%; 2026-10-05: 20%
| Engagement Manager | Paul Jarah | Category | Standard | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 46.72% | 1648 | 206 | 518160 | 276072 | -518160
Exemplar - BCG Business Case | Leadership | Aleksandar Vranesevic | Partner |  | 500 |  | 500 | 4000 | 248 |  | 0 |  | 0 | 0 | 0 | 50.4% | 112 | 14 | 56000 | 27776 | -56000 |  | 2025-05-19: 20%; 2025-05-26: 20%; 2025-06-02: 20%; 2025-06-09: 20%; 2025-06-16: 20%; 2025-06-23: 20%; 2025-06-30: 20%; 2025-07-07: 20%; 2025-07-14: 20%; 2025-07-21: 20%; 2025-07-28: 20%; 2025-08-04: 20%; 2025-08-11: 20%; 2025-08-18: 20%
Exemplar - BCG Business Case | Main Document / Engagement Lead | Paul Jarah | Director |  | 340 |  | 340 | 2720 | 189 |  | 0 |  | 0 | 0 | 0 | 44.41% | 284 | 35.5 | 96560 | 53676 | -96560 |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 90%; 2025-06-16: 60%; 2025-06-23: 20%; 2025-06-30: 20%; 2025-07-07: 20%; 2025-07-14: 20%; 2025-07-21: 20%; 2025-07-28: 40%; 2025-08-04: 40%; 2025-08-11: 40%; 2025-08-18: 40%
Exemplar - BCG Business Case | Attachment A - Costings | Hanan Asghar | Senior Manager |  | 290 |  | 290 | 2320 | 180 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Exemplar - BCG Business Case | Attachment B - Project Management Plan | Paul Jarah | Director |  | 340 |  | 340 | 2720 | 189 |  | 0 |  | 0 | 0 | 0 | 44.41% | 144 | 18 | 48960 | 27216 | -48960 |  | 2025-06-09: 10%; 2025-06-16: 40%; 2025-06-23: 40%; 2025-06-30: 40%; 2025-07-07: 40%; 2025-07-14: 40%; 2025-07-21: 30%; 2025-07-28: 30%; 2025-08-04: 30%; 2025-08-11: 30%; 2025-08-18: 30%
Exemplar - BCG Business Case | Attachment C - Risk Management Approach | Nathan Richards | Senior Manager |  | 290 |  | 290 | 2320 | 146 |  | 0 |  | 0 | 0 | 0 | 49.66% | 16 | 2 | 4640 | 2336 | -4640 |  | 2025-07-21: 20%; 2025-07-28: 20%
Exemplar - BCG Business Case | Attachment D - Risk Register | Nathan Richards | Senior Manager |  | 290 |  | 290 | 2320 | 146 |  | 0 |  | 0 | 0 | 0 | 49.66% | 40 | 5 | 11600 | 5840 | -11600 |  | 2025-07-21: 20%; 2025-07-28: 20%; 2025-08-04: 20%; 2025-08-11: 20%; 2025-08-18: 20%
Exemplar - BCG Business Case | Attachment E - Benefits Realisation Plan and Register | Hanan Asghar | Senior Manager |  | 290 |  | 290 | 2320 | 180 |  | 0 |  | 0 | 0 | 0 | 37.93% | 80 | 10 | 23200 | 14400 | -23200 |  | 2025-05-26: 40%; 2025-06-02: 40%; 2025-06-09: 40%; 2025-06-16: 40%; 2025-06-23: 40%
Exemplar - BCG Business Case | Attachment F - Solution Architecture | Phani Gollamudi | Director |  | 340 |  | 340 | 2720 | 198 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Exemplar - BCG Business Case | Attachment G - Business Process Models | Hanan Asghar | Senior Manager |  | 290 |  | 290 | 2320 | 180 |  | 0 |  | 0 | 0 | 0 | 37.93% | 80 | 10 | 23200 | 14400 | -23200 |  | 2025-05-26: 40%; 2025-06-02: 40%; 2025-06-09: 40%; 2025-06-16: 40%; 2025-06-23: 40%
Exemplar - BCG Business Case | Attachment H - Requirements / Benefit & Process | Nathan Richards | Senior Manager |  | 290 |  | 290 | 2320 | 146 |  | 0 |  | 0 | 0 | 0 | 49.66% | 480 | 60 | 139200 | 70080 | -139200 |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 60%; 2025-07-28: 60%; 2025-08-04: 60%; 2025-08-11: 60%; 2025-08-18: 60%
Exemplar - BCG Business Case | Attachment I - Quality Plan | Michelle Chant | Senior Manager |  | 290 |  | 290 | 2320 | 146 |  | 0 |  | 0 | 0 | 0 | 49.66% | 24 | 3 | 6960 | 3504 | -6960 |  | 2025-07-14: 10%; 2025-07-21: 10%; 2025-07-28: 10%; 2025-08-04: 10%; 2025-08-11: 10%; 2025-08-18: 10%
Exemplar - BCG Business Case | Attachment J - Governance Plan | Paul Jarah | Director |  | 340 |  | 340 | 2720 | 189 |  | 0 |  | 0 | 0 | 0 | 44.41% | 40 | 5 | 13600 | 7560 | -13600 |  | 2025-06-23: 20%; 2025-06-30: 20%; 2025-07-07: 20%; 2025-07-14: 20%; 2025-07-21: 20%
Exemplar - BCG Business Case | Attachment K - Assurance Plan | Paul Jarah | Director |  | 340 |  | 340 | 2720 | 189 |  | 0 |  | 0 | 0 | 0 | 44.41% | 40 | 5 | 13600 | 7560 | -13600 |  | 2025-06-23: 20%; 2025-06-30: 20%; 2025-07-07: 20%; 2025-07-14: 20%; 2025-07-21: 20%
Exemplar - BCG Business Case | Attachment L - Procurement Plan | Paul Jarah | Senior Manager |  | 290 |  | 290 | 2320 | 189 |  | 0 |  | 0 | 0 | 0 | 34.83% | 52 | 6.5 | 15080 | 9828 | -15080 |  | 2025-07-21: 10%; 2025-07-28: 30%; 2025-08-04: 30%; 2025-08-11: 30%; 2025-08-18: 30%
Exemplar - BCG Business Case | Attachment M - Cyber Security Plan | Akshay Gupta | Senior Manager |  | 290 |  | 290 | 2320 | 162.5 |  | 0 |  | 0 | 0 | 0 | 43.97% | 48 | 6 | 13920 | 7800 | -13920 |  | 2025-06-16: 40%; 2025-06-23: 40%; 2025-06-30: 40%
Exemplar - BCG Business Case | Attachment N - Change, Stakeholder, Management and Taining Plan | Michelle Chant | Senior Manager |  | 290 |  | 290 | 2320 | 146 |  | 0 |  | 0 | 0 | 0 | 49.66% | 72 | 9 | 20880 | 10512 | -20880 |  | 2025-07-14: 30%; 2025-07-21: 30%; 2025-07-28: 30%; 2025-08-04: 30%; 2025-08-11: 30%; 2025-08-18: 30%
Exemplar - BCG Business Case | Attachment O - Workforce Plan | Nathan Richards | Senior Manager |  | 290 |  | 290 | 2320 | 146 |  | 0 |  | 0 | 0 | 0 | 49.66% | 24 | 3 | 6960 | 3504 | -6960 |  | 2025-08-04: 20%; 2025-08-11: 20%; 2025-08-18: 20%
Exemplar - BCG Business Case | Project & Document Coordinator | Sian Davies | Senior Consultant |  | 212.5 |  | 212.5 | 1700 | 90 |  | 0 |  | 0 | 0 | 0 | 57.65% | 112 | 14 | 23800 | 10080 | -23800 |  | 2025-05-19: 20%; 2025-05-26: 20%; 2025-06-02: 20%; 2025-06-09: 20%; 2025-06-16: 20%; 2025-06-23: 20%; 2025-06-30: 20%; 2025-07-07: 20%; 2025-07-14: 20%; 2025-07-21: 20%; 2025-07-28: 20%; 2025-08-04: 20%; 2025-08-11: 20%; 2025-08-18: 20%
Exemplar - IT Review - $160k |  |  | Partner | Client Manager | 0 |  | 0 | [9 empty] | 32 | 4 | 0 |  |  |  | 2025-05-19: 10%; 2025-05-26: 10%; 2025-06-02: 10%; 2025-06-09: 10%; 2025-06-16: 10%; 2025-06-23: 10%; 2025-06-30: 10%; 2025-07-07: 10%
Exemplar - IT Review - $160k | Expert report |  | Senior Manager | Lead Consultant | 290 |  | 290 | [9 empty] | 320 | 40 | 92800 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%
Exemplar - IT Review - $160k | Engagement support and analysis |  | Senior Consultant | Support Consultant | 212.5 |  | 212.5 | [9 empty] | 320 | 40 | 68000 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%
Exemplar - ICT Business case: 8-12 weeks = $900K | Client Manager |  | Partner | Client Manager | 500 | 0% | 500 | [9 empty] | 144 | 18 | 72000 |  |  |  | 2025-05-19: 30%; 2025-05-26: 30%; 2025-06-02: 30%; 2025-06-09: 30%; 2025-06-16: 30%; 2025-06-23: 30%; 2025-06-30: 30%; 2025-07-07: 30%; 2025-07-14: 30%; 2025-07-21: 30%; 2025-07-28: 30%; 2025-08-04: 30%
Exemplar - ICT Business case: 8-12 weeks = $900K | Narrative, Main body, roadmap |  | Principal | Engagement Mgr/Lead Consultant | 340 | 0% | 340 | [9 empty] | 480 | 60 | 163200 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%; 2025-07-28: 100%; 2025-08-04: 100%
Exemplar - ICT Business case: 8-12 weeks = $900K | Tech design, requirements/features, arch current/future, cyber |  | Principal | Tech Lead | 340 | 0% | 340 | [9 empty] | 480 | 60 | 163200 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%; 2025-07-28: 100%; 2025-08-04: 100%
Exemplar - ICT Business case: 8-12 weeks = $900K | Reqmnts, process analysis, current/future |  | Senior Manager | Business Lead | 290 | 0% | 290 | [9 empty] | 480 | 60 | 139200 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%; 2025-07-28: 100%; 2025-08-04: 100%
Exemplar - ICT Business case: 8-12 weeks = $900K | Costings, benefits, (squad costings based on reqmts) |  | Senior Manager | CBA analyst | 290 | 0% | 290 | [9 empty] | 480 | 60 | 139200 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%; 2025-07-28: 100%; 2025-08-04: 100%
Exemplar - ICT Business case: 8-12 weeks = $900K | PMP, supporting docs |  | Manager | Business Analyst | 250 | 0% | 250 | [9 empty] | 480 | 60 | 120000 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%; 2025-07-28: 100%; 2025-08-04: 100%
Exemplar - ICT Business case: 8-12 weeks = $900K | Supporting docs, engagement support, project coords |  | Senior Consultant | Business Analyst | 212.5 | 0% | 212.5 | [9 empty] | 480 | 60 | 102000 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%; 2025-07-28: 100%; 2025-08-04: 100%
Exemplar - Mercury team (medium) - IT build $1M | Client Manager |  | Partner | Client Manager | 500 | 0% | 500 | [11 empty] | 52000 |  |  |  | 2025-05-19: 20%; 2025-05-26: 20%; 2025-06-02: 20%; 2025-06-09: 20%; 2025-06-16: 20%; 2025-06-23: 20%; 2025-06-30: 20%; 2025-07-07: 20%; 2025-07-14: 20%; 2025-07-21: 20%; 2025-07-28: 20%; 2025-08-04: 20%; 2025-08-11: 20%
Exemplar - Mercury team (medium) - IT build $1M | Delivery Manager |  | Principal | Delivery Manager | 340 | 0% | 340 | [11 empty] | 176800 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%; 2025-07-28: 100%; 2025-08-04: 100%; 2025-08-11: 100%
Exemplar - Mercury team (medium) - IT build $1M | Architect |  | Principal | Architect | 340 | 0% | 340 | [11 empty] | 176800 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%; 2025-07-28: 100%; 2025-08-04: 100%; 2025-08-11: 100%
Exemplar - Mercury team (medium) - IT build $1M | Developer |  | Senior Manager | Developer | 290 | 0% | 290 | [11 empty] | 150800 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%; 2025-07-28: 100%; 2025-08-04: 100%; 2025-08-11: 100%
Exemplar - Mercury team (medium) - IT build $1M | Data & Cyber |  | Senior Manager | Data & Cyber | 290 | 0% | 290 | [11 empty] | 150800 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%; 2025-07-28: 100%; 2025-08-04: 100%; 2025-08-11: 100%
Exemplar - Mercury team (medium) - IT build $1M | Integration |  | Senior Manager | Integration | 290 | 0% | 290 | [11 empty] | 150800 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%; 2025-07-28: 100%; 2025-08-04: 100%; 2025-08-11: 100%
Exemplar - Mercury team (medium) - IT build $1M | Dashboard & Viz |  | Senior Manager | Dashboard & Viz | 290 | 0% | 290 | [11 empty] | 150800 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%; 2025-07-28: 100%; 2025-08-04: 100%; 2025-08-11: 100%
Exemplar - ICT Procurement (medium): $240K | Client Manager |  | Partner | Client Manager | 500 | 0% | 500 | [9 empty] | 80 | 10 | 40000 |  |  |  | 2025-05-19: 20%; 2025-05-26: 20%; 2025-06-02: 20%; 2025-06-09: 20%; 2025-06-16: 20%; 2025-06-23: 20%; 2025-06-30: 20%; 2025-07-07: 20%; 2025-07-14: 20%; 2025-07-21: 20%
Exemplar - ICT Procurement (medium): $240K | Expert report |  | Senior Manager | Lead Consultant | 290 | 0% | 290 | [9 empty] | 400 | 50 | 116000 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%
Exemplar - ICT Procurement (medium): $240K | Engagement support and analysis |  | Senior Consultant | Support Consultant | 212.5 | 0% | 212.5 | [9 empty] | 400 | 50 | 85000 |  |  |  | 2025-05-19: 100%; 2025-05-26: 100%; 2025-06-02: 100%; 2025-06-09: 100%; 2025-06-16: 100%; 2025-06-23: 100%; 2025-06-30: 100%; 2025-07-07: 100%; 2025-07-14: 100%; 2025-07-21: 100%

## KPIs
KPIs | INITIAL POSITION | FINAL POSITION | COMMENTARY | NOTES
CX | N/A |  |  | Agree on the CX value for the engagement and record any exception against any particular team member(s) at the point of closure
Revenue Recognition |  |  |  | Enter in name and percentage of people to be recognised. Total % needs to add up to 100%. Percentage should be broken down by Find, Win, Deliver (Refer to guidance material for more instructions) Example: John Smith - 20% Find John Doe - 20% Win 20% Deliver Brandon Jones - 40% - Win
Financial: Budget $ ex GST | 0 | 0 |  | Explain any variance and the proposed treatment
Actual $ ex GST | N/A | 0
Variance $ ex GST | N/A | 0
PO Variance $ ex GST | 0 | 0

## Closing financials (hidden)
NOTES
INSERT FINAL POSITION (PRE-BALANCING - OPS TEAM) | INSERT FINAL POSITION (POST-BALANCING - OPS TEAM)
Screenshot of i-time Project Task Budget Report | Screenshot of i-time Project Task Budget Report

## Closure
CLOSURES
Reason for closure | Example: All deliverables completed and accepted. Note that further improvements to deliverables have been identified and handed over to Client for further actioning.
Key deliverables | Insert screenshot from Engagement SharePoint content for harvest folder
Client feedback | (Embed evidence if possible)
Client's Agreement to be referee | Yes, No, Possible
(Written evidence or provide comments) Comments:
capture names and details of people, eg RAIN behaviours
CLOSURE CHECKLIST
Activity | Who | Action taken / Result | Done
Reason for closure | Engagement manager | see above
Key deliverables for harvest | Engagement manager | see above
Client feedback | Engagement manager | see above
Client's Agreement to be referee | Engagement manager | see above
Update profiles (EM to remind team) | Entire team
Conduct a lessons learnt | Entire team
Write project brief (background, what we did, outcome) | Engagement manager
Add follow-on opportunities to KAM sales pipeline | Engagement manager
Provide feedback (up, down and sideways) | Entire team
Closure meeting | Engagement manager & COO

## Expenses (hidden)
EXPENSES
Date | Description | Amount (ex. GST) | Recoverable from Client | Billed to Client
Total |  | 0

## Time Plan HY (hidden)
Forecast Date | 2025-11-03 | [21 empty] | Monday Commencing (Select) | [32 empty] | Hypercare
Contract Start Date | 2025-11-03 | [8 empty] | Delivery | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492 | 493 | 494 | 495 | 496 | 497 | 498 | 499 | 500 | 501 | 502 | 503 | 504 | 505 | 506 | 507 | 508 | 509 | 510 | 511 | 512 | 513 | 514 | 515 | 516 | 517 | 518 | 519 | 520 | 521 | 522 | 523 | 524 | 525 | 526 | 527 | 528 | 529 | 530 | 531 | 532 | 533 | 534 | 535 | 536 | 537 | 538 | 539 | 540 | 541 | 542 | 543 | 544 | 545 | 546 | 547 | 548 | 549 | 550 | 551 | 552 | 553 | 554 | 555 | 556 | 557 | 558 | 559 | 560 | 561 | 562 | 563 | 564 | 565 | 566 | 567 | 568 | 569 | 570 | 571 | 572 | 573 | 574 | 575 | 576 | 577 | 578 | 579 | 580 | 581 | 582 | 583 | 584 | 585 | 586 | 587 | 588 | 589 | 590 | 591
Milestone | Deliverable | Resource | Charge Out Level | Job Role | Panel Hourly Rate $ ex-GST | Discount (%) | Discounted Hourly Rate $ ex GST | Panel Daily Rate $ ex-GST | Hourly Gross Cost $ | Budget Hours | Budget $ ex GST | Actual Hours as at 03-Nov | Charge $ ex GST | Balance $ ex GST (Budget - Charge) | Gross Cost $ ex GST | Gross Margin | Forecast hours | Forecast Days | Forecast $ ex GST | Forecast Gross Cost $ ex GST | Variance at completion (ex GST) | Variance at completion (%) | time axis 2025-11-03 to 2037-02-23
| Account Manager | Aleksandar Vranesevic | Panel | Software & ERP Marketplace | [18 empty] | 2025-12-22: 100%; 2025-12-29: 100%; 2026-01-26: 20%; 2026-03-09: 20%; 2026-03-30: 20%; 2026-04-06: 20%; 2026-04-20: 20%; 2026-06-01: 20%; 2026-06-08: 20%; 2026-10-05: 20%; 2026-12-21: 100%; 2026-12-28: 100%; 2027-01-25: 20%; 2027-03-08: 20%; 2027-03-22: 20%; 2027-03-29: 20%; 2027-04-26: 20%; 2027-05-31: 20%; 2027-06-14: 20%; 2027-10-04: 20%; 2027-12-20: 100%; 2027-12-27: 100%; 2028-01-24: 20%; 2028-03-13: 40%; 2028-03-20: 20%; 2028-04-24: 20%; 2028-05-29: 20%; 2028-06-12: 20%; 2028-10-02: 20%; 2028-12-25: 100%; 2029-01-01: 100%; 2029-01-22: 20%; 2029-03-12: 20%; 2029-03-26: 20%; 2029-04-02: 20%; 2029-04-23: 20%; 2029-05-28: 20%; 2029-06-11: 20%
| Engagement Manager | Alex Kocz | Category | Analysis, Design and COTS Development Services for a Software Acquisition and or Implementation | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 2992 | 374 | 701300 | 0 | -701300
M1 Discovery | 1.1 Detailed requirements, business process mapping complete and signed off | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 92 | 11.5 | 25300 |  | -25300 |  | 2025-11-03: 80%; 2025-11-10: 50%; 2025-11-17: 50%; 2025-11-24: 50%
M1 Discovery | 1.1 Detailed requirements, business process mapping complete and signed off | Contractor-Business/System Analyst | Qualified Practitioner |  | 190 |  | 190 | 1520 |  |  | 0 |  | 0 | 0 |  |  | 100 | 12.5 | 19000 |  | -19000 |  | 2025-11-03: 100%; 2025-11-10: 50%; 2025-11-17: 50%; 2025-11-24: 50%
M1 Discovery | 1.1 Detailed requirements, business process mapping complete and signed off | Contractor-Senior Architect | Experienced Practitioner | ServiceNow architect | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 100 | 12.5 | 27500 |  | -27500 |  | 2025-11-03: 100%; 2025-11-10: 50%; 2025-11-17: 50%; 2025-11-24: 50%
M1 Discovery | 1.1 Detailed requirements, business process mapping complete and signed off | Contractor-Developer | Junior Practitioner | ServiceNow developer | 165 |  | 165 | 1320 |  |  | 0 |  | 0 | 0 |  |  | 60 | 7.5 | 9900 |  | -9900 |  | 2025-11-03: 50%; 2025-11-10: 50%; 2025-11-17: 25%; 2025-11-24: 25%
M1 Discovery | 1.3 Detailed delivery plan and RACI of build and delivery meeting AGD Operating Model requirements | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 32 | 4 | 8800 |  | -8800 |  | 2025-11-03: 20%; 2025-11-10: 20%; 2025-11-17: 20%; 2025-11-24: 20%
M2A Build and delivery | 2.1 Build and data migration | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 272 | 34 | 74800 |  | -74800 |  | 2025-12-01: 50%; 2025-12-08: 50%; 2025-12-15: 50%; 2026-01-05: 50%; 2026-01-12: 50%; 2026-01-19: 50%; 2026-01-26: 40%; 2026-02-02: 50%; 2026-02-09: 50%; 2026-02-16: 50%; 2026-02-23: 50%; 2026-03-02: 50%; 2026-03-09: 40%; 2026-03-16: 50%
M2A Build and delivery | 2.1 Build and data migration | Contractor-Senior Architect | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 140 | 17.5 | 38500 |  | -38500 |  | 2025-12-01: 25%; 2025-12-08: 25%; 2025-12-15: 25%; 2026-01-05: 25%; 2026-01-12: 25%; 2026-01-19: 25%; 2026-01-26: 25%; 2026-02-02: 25%; 2026-02-09: 25%; 2026-02-16: 25%; 2026-02-23: 25%; 2026-03-02: 25%; 2026-03-09: 25%; 2026-03-16: 25%
M2A Build and delivery | 2.1 Build and data migration | Contractor-Change Manager | Qualified Practitioner |  | 190 |  | 190 | 1520 |  |  | 0 |  | 0 | 0 |  |  | 280 | 35 | 53200 |  | -53200 |  | 2025-12-01: 50%; 2025-12-08: 50%; 2025-12-15: 50%; 2026-01-05: 50%; 2026-01-12: 50%; 2026-01-19: 50%; 2026-01-26: 50%; 2026-02-02: 50%; 2026-02-09: 50%; 2026-02-16: 50%; 2026-02-23: 50%; 2026-03-02: 50%; 2026-03-09: 50%; 2026-03-16: 50%
M2A Build and delivery | 2.1 Build and data migration | Contractor-Developer | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 280 | 35 | 77000 |  | -77000 |  | 2025-12-01: 50%; 2025-12-08: 50%; 2025-12-15: 50%; 2026-01-05: 50%; 2026-01-12: 50%; 2026-01-19: 50%; 2026-01-26: 50%; 2026-02-02: 50%; 2026-02-09: 50%; 2026-02-16: 50%; 2026-02-23: 50%; 2026-03-02: 50%; 2026-03-09: 50%; 2026-03-16: 50%
M2A Build and delivery | 2.1 Build and data migration | Contractor-Developer | Junior Practitioner |  | 165 |  | 165 | 1320 |  |  | 0 |  | 0 | 0 |  |  | 280 | 35 | 46200 |  | -46200 |  | 2025-12-01: 50%; 2025-12-08: 50%; 2025-12-15: 50%; 2026-01-05: 50%; 2026-01-12: 50%; 2026-01-19: 50%; 2026-01-26: 50%; 2026-02-02: 50%; 2026-02-09: 50%; 2026-02-16: 50%; 2026-02-23: 50%; 2026-03-02: 50%; 2026-03-09: 50%; 2026-03-16: 50%
M2A Build and delivery | 2.1 Build and data migration | Contractor-Developer | Junior Practitioner |  | 165 |  | 165 | 1320 |  |  | 0 |  | 0 | 0 |  |  | 280 | 35 | 46200 |  | -46200 |  | 2025-12-01: 50%; 2025-12-08: 50%; 2025-12-15: 50%; 2026-01-05: 50%; 2026-01-12: 50%; 2026-01-19: 50%; 2026-01-26: 50%; 2026-02-02: 50%; 2026-02-09: 50%; 2026-02-16: 50%; 2026-02-23: 50%; 2026-03-02: 50%; 2026-03-09: 50%; 2026-03-16: 50%
| 2.1 Build and data migration | Contractor-Test Manager | Experienced Practitioner | [19 empty] | 2025-12-01: 25%; 2025-12-08: 25%; 2025-12-15: 25%; 2026-01-05: 25%; 2026-01-12: 25%; 2026-01-19: 25%; 2026-01-26: 25%; 2026-02-02: 25%; 2026-02-09: 25%; 2026-02-16: 25%; 2026-02-23: 25%; 2026-03-02: 25%; 2026-03-09: 25%; 2026-03-16: 25%
M2A Build and delivery
M2A Build and delivery | 2.2. Training | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner | [19 empty] | 2026-03-23: 50%; 2026-03-30: 50%; 2026-04-06: 50%
M2A Build and delivery | 2.2. Training | Contractor-Business/System Analyst | Qualified Practitioner | [19 empty] | 2026-03-23: 50%; 2026-03-30: 50%; 2026-04-06: 50%
M2A Build and delivery | 2.2. Training | Contractor-Developer | Junior Practitioner | [19 empty] | 2026-03-23: 25%; 2026-03-30: 25%; 2026-04-06: 25%
| 2.2. Training | Contractor-Change Manager | Qualified Practitioner
M2A Build and delivery
M2A Build and delivery | 2.3 Testing | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner | [19 empty] | 2026-04-13: 50%; 2026-04-20: 50%; 2026-04-27: 50%; 2026-05-04: 50%
M2A Build and delivery | 2.3 Testing | Contractor-Developer | Junior Practitioner | [19 empty] | 2026-04-13: 50%; 2026-04-20: 50%; 2026-04-27: 50%; 2026-05-04: 50%
M2A Build and delivery | 2.3 Testing | Contractor-Developer | Experienced Practitioner | [19 empty] | 2026-04-13: 50%; 2026-04-20: 50%; 2026-04-27: 50%; 2026-05-04: 50%
M2A Build and delivery | 2.3 Testing | Contractor-Test Manager | Experienced Practitioner | [19 empty] | 2026-04-13: 50%; 2026-04-20: 50%; 2026-04-27: 50%; 2026-05-04: 50%
M2A Build and delivery
M2A Build and delivery | 2.4 Go Live | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner | [19 empty] | 2026-05-11: 50%; 2026-05-18: 50%
M2A Build and delivery | 2.4 Go Live | Contractor-Developer | Junior Practitioner | [19 empty] | 2026-05-11: 50%; 2026-05-18: 50%
M2A Build and delivery | 2.4 Go Live | Contractor-Developer | Experienced Practitioner | [19 empty] | 2026-05-11: 50%; 2026-05-18: 50%
M2A Build and delivery | 2.4 Go Live | Contractor-Test Manager | Experienced Practitioner | [19 empty] | 2026-05-11: 50%; 2026-05-18: 50%
M2A Build and delivery | 2.5 Hypercare & 2.9 Handover | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 40 | 5 | 11000 |  | -11000 |  | 2026-05-25: 25%; 2026-06-01: 25%; 2026-06-08: 25%; 2026-06-15: 25%
M2A Build and delivery | 2.5 Hypercare & 2.9 Handover | Contractor-Developer | Junior Practitioner |  | 165 |  | 165 | 1320 |  |  | 0 |  | 0 | 0 |  |  | 80 | 10 | 13200 |  | -13200 |  | 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%
M2A Build and delivery | 2.5 Hypercare & 2.9 Handover | Contractor-Test Manager | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 40 | 5 | 11000 |  | -11000 |  | 2026-05-25: 25%; 2026-06-01: 25%; 2026-06-08: 25%; 2026-06-15: 25%
M2A Build and delivery
M2B AI Proof of Concept | 2.6 Detailed requirements, business process mapping complete and signed off | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 12 | 1.5 | 3300 |  | -3300 |  | 2025-11-24: 30%
M2B AI Proof of Concept | 2.6 Detailed requirements, business process mapping complete and signed off | Contractor-Business/System Analyst | Qualified Practitioner | [19 empty] | 2025-11-24: 50%
M2B AI Proof of Concept | 2.6 Detailed requirements, business process mapping complete and signed off | Contractor-Senior Architect | Experienced Practitioner | [19 empty] | 2025-11-24: 50%
M2B AI Proof of Concept | 2.6 Detailed requirements, business process mapping complete and signed off | Contractor-Developer | Junior Practitioner | [19 empty] | 2025-11-24: 25%
M2B AI Proof of Concept | [16 empty] | 0 | 0
M2B AI Proof of Concept | 2.7 Proof of Concept - including the delivery of an accuracy, return on investment, delivery plan to production and model upgrade plan | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 80 | 10 | 22000 |  | -22000 |  | 2026-01-12: 50%; 2026-01-19: 50%; 2026-01-26: 50%; 2026-02-02: 50%
M2B AI Proof of Concept | 2.7 Proof of Concept - including the delivery of an accuracy, return on investment, delivery plan to production and model upgrade plan | Contractor-Senior Architect | Experienced Practitioner | [19 empty] | 2026-01-12: 25%; 2026-01-19: 25%; 2026-01-26: 25%; 2026-02-02: 25%
M2B AI Proof of Concept | 2.7 Proof of Concept - including the delivery of an accuracy, return on investment, delivery plan to production and model upgrade plan | Contractor-Developer | Junior Practitioner | [19 empty] | 2026-01-12: 50%; 2026-01-19: 50%; 2026-01-26: 50%; 2026-02-02: 50%
M2B AI Proof of Concept | 2.8 Detailed evaluation report and delivery plan | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 40 | 5 | 11000 |  | -11000 |  | 2026-02-09: 50%; 2026-02-16: 50%
M2B AI Proof of Concept | 2.8 Detailed evaluation report and delivery plan | Contractor-Business/System Analyst | Qualified Practitioner | [19 empty] | 2026-02-09: 50%; 2026-02-16: 50%
M2B AI Proof of Concept | 2.8 Detailed evaluation report and delivery plan | Contractor-Senior Architect | Experienced Practitioner | [19 empty] | 2026-02-09: 50%; 2026-02-16: 50%
M2C Self-service portal | 2.9 Detailed requirements, business process mapping complete and signed off | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 24 | 3 | 6600 |  | -6600 |  | 2025-11-10: 30%; 2025-11-17: 30%
M2C Self-service portal | 2.9 Detailed requirements, business process mapping complete and signed off | Contractor-Business/System Analyst | Qualified Practitioner |  | 190 |  | 190 | 1520 |  |  | 0 |  | 0 | 0 |  |  | 40 | 5 | 7600 |  | -7600 |  | 2025-11-10: 50%; 2025-11-17: 50%
M2C Self-service portal | 2.9 Detailed requirements, business process mapping complete and signed off | Contractor-Senior Architect | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 40 | 5 | 11000 |  | -11000 |  | 2025-11-10: 50%; 2025-11-17: 50%
M2C Self-service portal | 2.9 Detailed requirements, business process mapping complete and signed off | Contractor-Developer | Junior Practitioner |  | 165 |  | 165 | 1320 |  |  | 0 |  | 0 | 0 |  |  | 20 | 2.5 | 3300 |  | -3300 |  | 2025-11-10: 25%; 2025-11-17: 25%
M2C Self-service portal
M2C Self-service portal | 2.10 Build/delivery of self-service portal | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 120 | 15 | 33000 |  | -33000 |  | 2025-12-01: 50%; 2025-12-08: 50%; 2025-12-15: 50%; 2025-12-22: 50%; 2025-12-29: 50%; 2026-01-05: 50%
M2C Self-service portal | 2.10 Build/delivery of self-service portal | Contractor-Senior Architect | Experienced Practitioner | [19 empty] | 2025-12-01: 25%; 2025-12-08: 25%; 2025-12-15: 25%; 2025-12-22: 25%; 2025-12-29: 25%; 2026-01-05: 25%
M2C Self-service portal | 2.10 Build/delivery of self-service portal | Contractor-Developer | Junior Practitioner | [19 empty] | 2025-12-01: 50%; 2025-12-08: 50%; 2025-12-15: 50%; 2025-12-22: 50%; 2025-12-29: 50%; 2026-01-05: 50%
| 2.10 Build/delivery of self-service portal | Contractor-Developer | Experienced Practitioner | [19 empty] | 2025-12-01: 50%; 2025-12-08: 50%; 2025-12-15: 50%; 2025-12-22: 50%; 2025-12-29: 50%; 2026-01-05: 50%
| 2.10 Build/delivery of self-service portal | Contractor-Test Manager | Experienced Practitioner | [19 empty] | 2025-12-01: 25%; 2025-12-08: 25%; 2025-12-15: 25%; 2025-12-22: 25%; 2025-12-29: 25%; 2026-01-05: 25%
M2C Self-service portal
M2C Self-service portal | 2.11 Training | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner | [19 empty] | 2026-03-23: 50%; 2026-03-30: 50%
M2C Self-service portal | 2.11 Training | Contractor-Business/System Analyst | Qualified Practitioner | [19 empty] | 2026-03-23: 50%; 2026-03-30: 50%
M2C Self-service portal | 2.11 Training | Contractor-Developer | Junior Practitioner | [19 empty] | 2026-03-23: 50%; 2026-03-30: 50%
| 2.11 Training | Contractor-Change Manager | Qualified Practitioner | [19 empty] | 2026-03-23: 50%; 2026-03-30: 50%
M2C Self-service portal | 2.12 Testing: including testing plan and UAT requirements | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 140 | 17.5 | 38500 |  | -38500 |  | 2026-04-20: 50%; 2026-04-27: 50%; 2026-05-04: 50%; 2026-06-08: 100%; 2026-06-15: 100%
M2C Self-service portal | 2.12 Testing: including testing plan and UAT requirements | Contractor-Developer | Junior Practitioner | [19 empty] | 2026-04-20: 50%; 2026-04-27: 50%; 2026-05-04: 50%
| 2.12 Testing: including testing plan and UAT requirements | Contractor-Developer | Junior Practitioner | [19 empty] | 2026-04-20: 50%; 2026-04-27: 50%; 2026-05-04: 50%
M2C Self-service portal | 2.12 Testing: including testing plan and UAT requirements | Contractor-Test Manager | Experienced Practitioner | [19 empty] | 2026-04-20: 50%; 2026-04-27: 50%; 2026-05-04: 50%
M2C Self-service portal
M2C Self-service portal | 2.4 Go Live | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner | [19 empty] | 2026-05-11: 50%; 2026-05-18: 50%
M2C Self-service portal | 2.4 Go Live | Contractor-Developer | Junior Practitioner | [19 empty] | 2026-05-11: 50%; 2026-05-18: 50%
M2C Self-service portal | 2.4 Go Live | Contractor-Developer | Experienced Practitioner | [19 empty] | 2026-05-11: 50%; 2026-05-18: 50%
M2C Self-service portal | 2.4 Go Live | Contractor-Test Manager | Experienced Practitioner | [19 empty] | 2026-05-11: 50%; 2026-05-18: 50%
M2C Self-service portal
M3 Implementation of AI | 3.1 AI Build | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 220 | 27.5 | 60500 |  | -60500 |  | 2026-02-23: 50%; 2026-03-02: 50%; 2026-03-09: 50%; 2026-03-16: 100%; 2026-03-23: 50%; 2026-03-30: 50%; 2026-06-08: 100%; 2026-06-15: 100%
M3 Implementation of AI | 3.1 AI Build | Contractor-Senior Architect | Experienced Practitioner | [19 empty] | 2026-02-23: 50%; 2026-03-02: 50%; 2026-03-09: 50%; 2026-03-16: 100%; 2026-03-23: 50%; 2026-03-30: 50%
M3 Implementation of AI | 3.1 AI Build | Contractor-Developer | Junior Practitioner | [19 empty] | 2026-02-23: 50%; 2026-03-02: 50%; 2026-03-09: 50%; 2026-03-16: 100%; 2026-03-23: 50%; 2026-03-30: 50%
| 3.1 AI Build | Contractor-Test Manager | Experienced Practitioner | [19 empty] | 2026-02-23: 50%; 2026-03-02: 50%; 2026-03-09: 50%; 2026-03-16: 100%; 2026-03-23: 50%; 2026-03-30: 50%
M3 Implementation of AI
M3 Implementation of AI | 3.2 Training | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner | [19 empty] | 2026-04-06: 50%
M3 Implementation of AI | 3.2 Training | Contractor-Business/System Analyst | Qualified Practitioner | [19 empty] | 2026-04-06: 50%
M3 Implementation of AI | 3.2 Training | Contractor-Developer | Junior Practitioner |  | 165 |  | 165 | 1320 |  |  | 0 |  | 0 | 0 |  |  | 20 | 2.5 | 3300 |  | -3300 |  | 2026-04-06: 50%
M3 Implementation of AI | 3.2 Training | Contractor-Change Manager | Qualified Practitioner | [19 empty] | 2026-04-06: 50%
M3 Implementation of AI
M3 Implementation of AI | 3.3 Testing: including testing plan and UAT requirements | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner | [19 empty] | 2026-04-20: 50%; 2026-04-27: 50%
M3 Implementation of AI | 3.3 Testing: including testing plan and UAT requirements | Contractor-Developer | Junior Practitioner | [19 empty] | 2026-04-20: 50%; 2026-04-27: 50%
M3 Implementation of AI | 3.3 Testing: including testing plan and UAT requirements | Contractor-Developer | Junior Practitioner | [19 empty] | 2026-04-20: 50%; 2026-04-27: 50%
M3 Implementation of AI | 3.3 Testing: including testing plan and UAT requirements | Contractor-Test Manager | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
M3 Implementation of AI | [16 empty] | 0 | 0
M3 Implementation of AI | 2.4 Go Live | Contractor-Delivery Manager/PM/Scrum Master/Scheduler | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 40 | 5 | 11000 |  | -11000 |  | 2026-05-11: 50%; 2026-05-18: 50%
M3 Implementation of AI | 2.4 Go Live | Contractor-Developer | Junior Practitioner |  | 165 |  | 165 | 1320 |  |  | 0 |  | 0 | 0 |  |  | 40 | 5 | 6600 |  | -6600 |  | 2026-05-11: 50%; 2026-05-18: 50%
M3 Implementation of AI | 2.4 Go Live | Contractor-Developer | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 40 | 5 | 11000 |  | -11000 |  | 2026-05-11: 50%; 2026-05-18: 50%
M3 Implementation of AI | 2.4 Go Live | Contractor-Test Manager | Experienced Practitioner |  | 275 |  | 275 | 2200 |  |  | 0 |  | 0 | 0 |  |  | 40 | 5 | 11000 |  | -11000 |  | 2026-05-11: 50%; 2026-05-18: 50%
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0

## Variable
Client Name | VAT | VAT Lead | Names | Name | Gross Cost | JID | Schedule Start | Schedule End | Team | Comments | Location | Panel | Category | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Mondays | ACT Public Holidays | Panel | Category List | Level_List
AAT - Administrative Appeals Tribunal | Growth | Aleksandar Vranesevic | Aleksandar Vranesevic | Aaron Riddell | 100 | CO2 |  |  | CSD |  |  | Reason Group - Standard Rates | Market Rates | 1320 | 1520 | 1960 | 2440 | 3160 | 3960 | [6 empty] | Consultant | Senior Consultant | Manager | Senior Manager | Director | Partner | [6 empty] | 2024-10-21 |  | ACT Govt - Professional and Consulting Services Panel |  | Level 1
ABC - Australian Broadcasting Corporation | Growth | Aleksandar Vranesevic | Alex Kocz | Aaron Yang | 130 | EN3 |  |  | CSD |  |  | Digital Marketplace | Strategy and Policy | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2024-10-28 |  | Alex Kocz - Custom Rates |  | Level 2
ABS - Australian Bureau of Statistics | Growth | Aleksandar Vranesevic | Anil Kinagi | Abdul Mohammad | 147 | 0 | 45628 | 46326 | CSD |  |  | Digital Marketplace | Change and Transformation | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2024-11-04 |  | Boston Consulting Group (BCG) - teaming rates |  | Level 3
ACC - Australia Competition and Consumer Commission | Growth | Aleksandar Vranesevic | Arjun Wariar | Abhinav Arya | 193 | 0 |  |  | CSD |  |  | Digital Marketplace | Agile delivery and Governance | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2024-11-11 |  | DAFF DBD DM-26233 - Contractor micropanel |  | Level 4
ACI - Australian Criminal Intelligence Commission | Growth | Scott Foley | Hadas Yehezkel | Adam Harris | 193 | 0 |  |  | CSD |  |  | Digital Marketplace | Digital sourcing and ICT procurement | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2024-11-18 |  | DAFF STEPS - Advisory micropanel |  | Level 5
ACM - Australian Communications and Media Authority | Growth | Aleksandar Vranesevic | Joelle Blake | Adeel Rtiaz Qadri | 125 | 0 |  |  | CSD |  |  | Digital Marketplace | ICT risk management and audit activities | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2024-11-25 |  | Defence - ICT Provider Arrangement (ICTPA) |  | Level 6
ACR - Accenture | Growth | Scott Foley | Lacy Pejcinovic | Adi Mukherjee | 189.66 | 0 |  |  | CSD |  |  | Digital Marketplace | User research and Design | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2024-12-02 |  | Department of Finance - Management Advisory Services
ACS - Australian Commission on Safety and Quality in Health Care | Growth | Aleksandar Vranesevic | Mark Volpato | Ahmed Shaikh | 152.91 | 0 | 45880 | 45991 | CSD |  |  | Digital Marketplace | Software engineering and Development | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2024-12-09 |  | Digital Marketplace
ACT - ACT Government | Growth | Aleksandar Vranesevic | Michelle Chant | Ajay Peddu | 145 | 0 |  |  | CSD |  |  | Digital Marketplace | Marketing, Communications and Engagement | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2024-12-16 |  | Digital Marketplace 2
ADE - Australian Diabetes Educators Association | Growth | Aleksandar Vranesevic | Nathan Richards | Ajit Thomas | 200 | EN4 |  |  | CSD |  |  | Digital Marketplace | Support and Operations | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2024-12-23 | 100% | DOH SME Supplementary Teams Arrangement (STA) - micropanel
ADH - Australian Digital Health Agency | Growth | Aleksandar Vranesevic | Phani Gollamudi | Akash Goyal | 144.17 | 0 | 45888 | 46059 | CSD | XPT |  | Digital Marketplace | Data science | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2024-12-30 | 100% | Infosys - teaming rates
AEC - Australian Electoral Commission | Growth | Aleksandar Vranesevic | Richard Ryan | Akshay Gupta | 192.33 | 0 | 45707 | 46045 | CSD | SAU has a lower rate of $162.5, rest is at $192.33 |  | Digital Marketplace | Platforms integration | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2025-01-06 |  | Lab3 x AFMA DM-26175 micropanel - teaming rates
AFM - Australian Fisheries Management Authority | Growth | Aleksandar Vranesevic | Scott Foley | Aleksandar Vranesevic | 248 | BD7 |  |  | CAS |  |  | Digital Marketplace | Service Integration and Management | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2025-01-13 |  | Reason Group - Standard Rates
AFP - Australian Federal Police | Growth | Aleksandar Vranesevic | Sian Davies | Alex Kocz | 248 | DM7 |  |  | CSD |  |  | Digital Marketplace | Cyber security | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2025-01-20 |  | Research and Evaluation Services Panel (RES)
AFS - Australian Financial Security Authority | Growth | Aleksandar Vranesevic | Siddhartha Sengupta | Alicia Lillington | 170.96 | 0 |  |  | CSD |  |  | Digital Marketplace | Emerging technologies | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2025-01-27 | 20% | SAP Professional Services Standing Offer Arrangement
AGD - Attorney-General's Department | Growth | Scott Foley | Stacy Bosel | Alison Kidd | 173.17 | 0 | 45967 | 45985 | CSD |  |  | Digital Marketplace | ICT systems integration | 1320 | 1520 | 1700 | 2000 | 2320 | 2720 | 4000 | 4550 |  |  |  |  | Associate | Consultant | Senior Consultant | Manager | Senior Manager | Principal Consultant | Partner | Senior Partner |  |  |  |  | 2025-02-03 |  | Software & ERP Marketplace
AGS - Australian Government Solicitor | Growth | Aleksandar Vranesevic | Tim Kreukniet | Amarnath Rasineni | 121 | 0 |  |  | CSD |  |  | Software & ERP Marketplace | Analysis, Design and COTS Development Services for a Software Acquisition and or Implementation | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Junior Practitioner | Qualified Practitioner | Experienced Practitioner | Discipline Specialist | Discipline Expert | [7 empty] | 2025-02-10 |  | Tech Mahindra - teaming rates
AHR - Australian Human Rights Commission | Growth | Aleksandar Vranesevic | William Scheer | Amit Chawla | 192.33 | 0 | 45894 | 45933 | CSD |  | ACT | Software & ERP Marketplace | Software Integration, Implementation, Change Management and Training | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Junior Practitioner | Qualified Practitioner | Experienced Practitioner | Discipline Specialist | Discipline Expert | [7 empty] | 2025-02-17
AIH - Australian Institute of Health and Welfare | Growth | Aleksandar Vranesevic | Zoe Haseler | Amit Pratap | 146.92 | 0 | 45670 | 46393 | CSD | New rates updated for Jan 2026 onwards |  | Software & ERP Marketplace | Data Migration and Conversion | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Junior Practitioner | Qualified Practitioner | Experienced Practitioner | Discipline Specialist | Discipline Expert | [7 empty] | 2025-02-24
AIR - Airservices Australia | Growth | Aleksandar Vranesevic |  | Andrea Milutinovic | 129 | DM4 |  |  | CSD |  |  | Software & ERP Marketplace | Software and System Testing | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Junior Practitioner | Qualified Practitioner | Experienced Practitioner | Discipline Specialist | Discipline Expert | [7 empty] | 2025-03-03
AMS - Australian Maritime Safety Authority | Growth | Aleksandar Vranesevic |  | Andrew Watts | 151 | EN5 | 46083 |  |  |  |  | Software & ERP Marketplace | Software and System Maintenance and Support | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Junior Practitioner | Qualified Practitioner | Experienced Practitioner | Discipline Specialist | Discipline Expert | [7 empty] | 2025-03-10 | 20%
ANA - Australian National Audit Office | Growth | Aleksandar Vranesevic |  | Aniket Edakhe | 204.35 | 0 | 45474 | 46111 | CSD | 25/6: Base cost updated for 1 July 2025 for SAU, $182.95 for SRO. |  | Software & ERP Marketplace | Cyber Security | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Junior Practitioner | Qualified Practitioner | Experienced Practitioner | Discipline Specialist | Discipline Expert | [7 empty] | 2025-03-17
ANS - Australian Nuclear Science and Technology Organisation | Growth | Aleksandar Vranesevic |  | Anil Kinagi | 245 | DM6 |  |  | CSD |  |  | Department of Finance - Management Advisory Services | Corporate | 1641.25 | 1835.57 | 2159.64 | 2505.11 | 2937.04 | 4232.82 | [6 empty] | Consultant | Senior Consultant | Manager | Senior Manager | Principal | Partner / Associate Partner | [6 empty] | 2025-03-24
APO - Australian Passport Office | Growth | Aleksandar Vranesevic |  | Anita Wong | 100 | 0 |  |  | CSD |  |  | Department of Finance - Management Advisory Services | Commercial | 1425.28 | 1641.25 | 1835.57 | 2159.64 | 2937.04 | 4232.82 | [6 empty] | Consultant | Senior Consultant | Manager | Senior Manager | Principal | Partner / Associate Partner | [6 empty] | 2025-03-31
APR - Australian Prudential Regulation Authority | Growth | Aleksandar Vranesevic |  | Ankit Jain | 176.31 | 0 |  |  | CSD |  |  | Research and Evaluation Services Panel (RES) | Evaluation Services | 1823.4 | 2431.2 | 2735.1 | 3039 | 4558.5 | [7 empty] | Consultant | Manager/ Senior Consultant | Senior Manager | Principal | Partner/Associate Partner | [7 empty] | 2025-04-07
APS - Australian Public Service Commission | Growth | Aleksandar Vranesevic |  | Ankit Srivastava | 186.99 | 0 | 45474 | 46203 | CSD | 25/6: Base cost updated for 1 July 2025 |  | Research and Evaluation Services Panel (RES) | User-Centred Design Services | 1823.4 | 2431.2 | 2735.1 | 3039 | 4558.5 | [7 empty] | Consultant | Manager/ Senior Consultant | Senior Manager | Principal | Partner/Associate Partner | [7 empty] | 2025-04-14 | 20%
APV - Australian Pesticides and Veterinary Medicines Authority | Growth | Aleksandar Vranesevic |  | Arinjay Singh | 145 | 0 |  |  | CSD |  |  | ACT Govt - Professional and Consulting Services Panel | Strategic Business Advice | 2112.6545 | 2811.4182 | 3164.9455 | 3518.4 | 5277.6 | [7 empty] | Consultant | Manager/ Senior Consultant | Senior Manager | Principal | Partner/Associate Partner | [7 empty] | 2025-04-21 | 40%
ARC - Australian Research Council | Growth | Aleksandar Vranesevic |  | Arjun Wariar | 245 | DM6 |  |  | CSD |  |  | ACT Govt - Professional and Consulting Services Panel | Human Resources Services | 1298.8364 | 1750.9818 | 1948.2909 | 2334.6182 | 3518.4 | [7 empty] | Consultant | Manager/ Senior Consultant | Senior Manager | Principal | Partner/Associate Partner | [7 empty] | 2025-04-28
ARE - Australian Renewable Energy Agency | Growth | Aleksandar Vranesevic |  | Arthur Rodos | 177 | 0 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Enterprise IT Governance | 0 | 0 | 0 | 0 | 1799.27 | 2072.28 | 2646.37 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-05-05
ARP - Australian Radiation Protection and Nuclear Safety Agency (ARPANSA) | Growth | Aleksandar Vranesevic |  | Ash Beauman | 225 | EN5 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Strategic Planning | 0 | 0 | 0 | 0 | 1863.96 | 2133.58 | 2684.1 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-05-12
ASD - Australian Signals Directorate | Growth | Aleksandar Vranesevic |  | Asit Deshpande | 186.99 | 0 | 45474 | 46203 | CSD | 27/6: Rates increased for 1 July 2025 |  | Defence - ICT Provider Arrangement (ICTPA) | Information Governance | 0 | 0 | 0 | 1662.28 | 1955.21 | 2348.8 | 2934.2 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-05-19
ASI - Australian Securities and Investments Commission | Growth | Aleksandar Vranesevic |  | Balachandar Mohan | 161 | 0 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Information System Coordination | 0 | 0 | 0 | 0 | 0 | 2107.08 | 2474.8 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-05-26
ASQ - Australian Skills Quality Authority (National VET Regulator) | Growth | Aleksandar Vranesevic |  | Ben Cairns | 202 | DM6 | 45923 | 46288 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Information Security | 0 | 0 | 1164.94 | 1464.57 | 1759.69 | 2264.26 | 2657.56 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-06-02 | 20%
ATI - Australian Trade and Investment Commission | Growth | Aleksandar Vranesevic |  | Benjamin Wolyan | 161 | 0 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Information Assurance | 0 | 0 | 0 | 0 | 1484.38 | 1778.91 | 2148.72 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-06-09 | 20%
ATO - Australian Taxation Office | Growth | William Scheer |  | Bradley Burge | 151 | EN5 | 45978 |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Analytics | 0 | 0 | 1177.94 | 1440.55 | 1743.87 | 2021.26 | 2335.73 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-06-16
ATS - Australian Transport Safety Bureau | Growth | Aleksandar Vranesevic |  | Brett Azzopardi | 190.63 | 0 | 45950 | 46112 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Data Visualisation | 0 | 0 | 0 | 1262.6 | 1420.08 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-06-23
BCG - Boston Consulting Group | Growth | Aleksandar Vranesevic |  | Chimere Elele | 0 | OP5 |  |  | OPS |  |  | Defence - ICT Provider Arrangement (ICTPA) | Information Content Publishing | 778.7 | 895.96 | 1028.83 | 1197.22 | 1388.85 | 1637.61 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-06-30
BOM - Bureau of Meteorology | Growth | Aleksandar Vranesevic |  | Chris Lu | 131.07 | 0 | 45474 | 46059 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Consultancy | 0 | 0 | 0 | 0 | 1978.62 | 2317.69 | 2683.48 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-07-07
CAS - Civil Aviation Safety Authority (CASA) | Growth | Aleksandar Vranesevic |  | Colton Goodear | 0 | PS2 |  |  | OPS |  |  | Defence - ICT Provider Arrangement (ICTPA) | Specialist Advice | 0 | 0 | 0 | 1818.11 | 2283.2 | 2709.7 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-07-14
CER - Clean Energy Regulator | Growth | Scott Foley |  | Contingency | 0 |  |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | IT Management | 0 | 0 | 0 | 0 | 1778.79 | 2191.52 | 2696.79 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-07-21
CMI - Coal Mining industry (Long Service Leave Funding) Corporation | Growth | Aleksandar Vranesevic |  | Contractor-Architect | 161 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Financial Management | 0 | 0 | 0 | 1488.41 | 1687.86 | 2007.76 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-07-28
COS - ConceptSix | Growth | Aleksandar Vranesevic |  | Contractor-Architect-Guru | 236 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Innovation | 0 | 0 | 0 | 0 | 2336.57 | 2681.13 | 2858.61 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-08-04
CRI - Crimtrac Agency | Growth | Aleksandar Vranesevic |  | Contractor-Architect-Lead | 214 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Business Process Improvement | 0 | 0 | 0 | 0 | 1602.7 | 1795.81 | 2216.69 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-08-11
CSC - Commonwealth Superannuation Corporation | Growth | Aleksandar Vranesevic |  | Contractor-Architect-Mid | 161 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Enterprise & Business Architecture | 0 | 0 | 0 | 0 | 1767.67 | 2070.9 | 2425.15 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-08-18
CSI - Commonwealth Scientific and Industrial Research Organisation | Growth | Aleksandar Vranesevic |  | Contractor-Architect-Senior | 193 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Business Risk Management | 0 | 0 | 0 | 1502.26 | 1714.94 | 2237.91 | 2623.05 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-08-25
DAF - Department of Agriculture, Fisheries and Forestry | DAFF | Joelle Blake |  | Contractor-Business/System Analyst-Junior | 107 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Sustainability | 0 | 0 | 0 | 1507.83 | 1707.33 | 2247.37 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-09-01
DAU - Dairy Australia | Growth | Aleksandar Vranesevic |  | Contractor-Business/System Analyst-Lead | 193 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Knowledge Management | 0 | 939.12 | 1186.32 | 1342.44 | 1501.36 | 1785.58 | 2093.79 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-09-08
DCC - Department of Climate Change, Energy, the Environment and Water | Growth | Scott Foley |  | Contractor-Business/System Analyst-Mid | 139 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Demand Management | 0 | 0 | 0 | 0 | 1691.25 | 1973.85 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-09-15
DFA - Department of Foreign Affairs and Trade | Growth | Aleksandar Vranesevic |  | Contractor-Business/System Analyst-Senior | 161 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Emerging Technology Monitoring | 0 | 0 | 0 | 1628.21 | 1850.85 | 2270.11 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-09-22
DHA - Department of Home Affairs | Growth | Aleksandar Vranesevic |  | Contractor-Change Manager-Junior/Analyst | 107 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Continuity Management | 0 | 0 | 0 | 1549.92 | 1943.11 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-09-29
DoD - Department of Defence | Growth | William Scheer |  | Contractor-Change Manager-Lead | 193 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Network Planning | 0 | 0 | 0 | 0 | 1292.58 | 1739.64 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-10-06 | 20%
DOF - Department of Finance | Growth | Scott Foley |  | Contractor-Change Manager-Mid | 145 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Solution Architecture | 0 | 0 | 0 | 1523 | 1737.12 | 2092.51 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-10-13
DOH - Department of Health, Disability and Ageing | Other | Anil Kinagi |  | Contractor-Change Manager-Senior | 161 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Data Management | 0 | 1031.57 | 1177.94 | 1440.55 | 1743.87 | 2037.12 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-10-20
DPS - Department of Parliamentary Services | Growth | Aleksandar Vranesevic |  | Contractor-Cost/Benefit/Financial Analyst-Lead/Manager | 177 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Methods & Tools | 0 | 0 | 1156.02 | 1399.36 | 1729.83 | 2192.15 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-10-27
DSS - Department of Social Services | Growth | Aleksandar Vranesevic |  | Contractor-Cost/Benefit/Financial Analyst-Mid | 139 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Portfolio Management | 0 | 0 | 0 | 0 | 1684.18 | 2061.15 | 2529.73 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-11-03
DTA - Digital Transformation Agency | Growth | Aleksandar Vranesevic |  | Contractor-Cost/Benefit/Financial Analyst-Senior | 161 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Programme Management | 0 | 0 | 0 | 0 | 0 | 2246.94 | 2748.52 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-11-10
DVA - Department of Veterans' Affairs | Growth | Aleksandar Vranesevic |  | Contractor-Cyber-Analyst | 145 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Project Management | 0 | 0 | 0 | 1403.3 | 1688.67 | 2132.96 | 2703.79 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-11-17
EDU - Department of Education | Growth | Aleksandar Vranesevic |  | Contractor-Cyber-Engineer | 161 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Portfolio, Programme and Project Support | 0 | 719.03 | 956.39 | 1185.99 | 1592.34 | 1813.22 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-11-24
EMP - Department of Employment | Growth | Scott Foley |  | Contractor-Cyber-Lead Engineer | 214 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Business Analysis | 0 | 0 | 1050.76 | 1288.06 | 1546.38 | 1886.14 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-12-01
EPI - Epicon | Growth | Scott Foley |  | Contractor-Cyber-Senior Engineer | 193 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Requirements Definition and Management | 0 | 1030.6 | 1221.22 | 1465.46 | 1721.12 | 2052.29 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-12-08
EUS - Epi-use | Growth | Scott Foley |  | Contractor-Data Analyst-Lead | 175 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Business Process Testing | 0 | 0 | 0 | 1040.92 | 1373.37 | 1592.99 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-12-15
EYA - Ernst & Young | Growth | Scott Foley |  | Contractor-Data Analyst-Mid | 118 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Change Implementation Planning and Management | 0 | 0 | 0 | 0 | 1701.1 | 2103.85 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-12-22 | 100%
FCA - Federal Court of Australia | Growth | Aleksandar Vranesevic |  | Contractor-Data Analyst-Senior | 150 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Organisational Design and Implementation | 0 | 0 | 0 | 0 | 1468.46 | 1863.5 | 2086 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2025-12-29 | 100%
FWC - Fair Work Commission | Growth | Aleksandar Vranesevic |  | Contractor-Data Engineer/Data Scientist-Mid | 161 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Benefits Management | 0 | 0 | 0 | 0 | 1957.24 | 2212.14 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-01-05
FWO - Office of the Fair Work Ombudsman | Other | Anil Kinagi |  | Contractor-Data Engineering/Scientist-Senior | 177 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Business Modelling | 0 | 876.17 | 1045.34 | 1266.88 | 1499.53 | 1862.67 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-01-12
GBR - Great Barrier Reef Marine Park Authority | Growth | Aleksandar Vranesevic |  | Contractor-Data Modeller | 150 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Organisational Capability Development | 0 | 0 | 0 | 0 | 1541.42 | 1878.71 | 2118.43 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-01-19
GEO - Geoscience Australia | Growth | Aleksandar Vranesevic |  | Contractor-Delivery Manager/PM-Mid | 155 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Systems Development Management | 0 | 0 | 0 | 0 | 1737.71 | 1941.05 | 2416.86 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-01-26 | 20%
HAU - Hearing Australia | Growth | Alex Kocz |  | Contractor-Delivery Manager/PM-Senior | 198 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Data Modelling & Design | 0 | 1031.57 | 1177.94 | 1440.55 | 1743.87 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-02-02
IBA - Indigenous Business Australia | Growth | Aleksandar Vranesevic |  | Contractor-Developer-Junior | 118 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Systems Design | 0 | 0 | 0 | 1209.81 | 1543.43 | 1878.47 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-02-09
IHA - Independent Health and Aged Care Pricing Authority | Growth | Aleksandar Vranesevic |  | Contractor-Developer-Lead/Technical Lead | 193 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Network Design | 0 | 0 | 0 | 0 | 1302.09 | 1738.64 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-02-16
IND - Department of Industry, Innovation and Science | Other | Anil Kinagi |  | Contractor-Developer-Mid | 145 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Database Design | 0 | 0 | 1060.02 | 1289.31 | 1637.36 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-02-23
INF - Department of Infrastructure, Transport, Regional Development, Communications and the Arts | Growth | Scott Foley |  | Contractor-Developer-Senior | 161 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Programming/Software Development | 0 | 803.29 | 1001.88 | 1188.68 | 1475.46 | 1605.07 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-03-02
IPA - IP Australia | Growth | Aleksandar Vranesevic |  | Contractor-DevOps Engineer-Mid | 161 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Real-time/Embedded Systems Development | 0 | 907.06 | 1114.17 | 1331.83 | 1566.59 | 1641.94 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-03-09 | 20%
ISY - Infosys | VIC | Alex Kocz |  | Contractor-DevOps Engineer-Senior | 180 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Animation Development | 0 | 0 | 1122.31 | 1391.29 | 1774.95 | 2160.23 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-03-16
LAB - LAB3 | Growth | William Scheer |  | Contractor-Program/Delivery Director | 225 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Safety Engineering | 0 | 0 | 1529.36 | 1794.32 | 1937.78 | 2308.09 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-03-23
MDB - Murray-Darling Basin Authority | Growth | Aleksandar Vranesevic |  | Contractor-Project Support/Coordinator-Junior | 75 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Software Design | 0 | 847.68 | 1018.58 | 1259.89 | 1559.79 | 1852.12 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-03-30 | 20%
MED - MedPass | Growth | Aleksandar Vranesevic |  | Contractor-Project Support/Coordinator-Mid | 100 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Information Content Authoring | 946.53 | 1094.45 | 1211.29 | 1352.63 | 1485.24 | 1844.32 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-04-06 | 20%
NAA - National Archives of Australia | Growth | Aleksandar Vranesevic |  | Contractor-Project Support/Coordinator-Senior | 118 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Testing | 597.78 | 683.87 | 886.39 | 1090.44 | 1298.33 | 1729.75 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-04-13
NAF - Northern Australia Infrastructure Facility | Growth | Aleksandar Vranesevic |  | Contractor-Scrum Master-Junior | 110 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | User Research | 0 | 0 | 1086.27 | 1290.21 | 1738.13 | 1962.41 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-04-20 | 20%
NAI - National Accreditation Authority for Translators and Interpreters | Growth | Aleksandar Vranesevic |  | Contractor-Scrum Master-Mid | 130 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | User Experience Analysis | 0 | 0 | 1027.43 | 1206.31 | 1717.83 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-04-27
NBA - National Blood Authority | Growth | Aleksandar Vranesevic |  | Contractor-Scrum Master-Senior | 150 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | User Experience Design | 0 | 0 | 975.92 | 1209.81 | 1543.43 | 1878.47 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-05-04
NCA - National Capital Authority | Growth | Aleksandar Vranesevic |  | Contractor-Service Designer/UI/UX-Lead | 177 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | User Experience Evaluation | 0 | 942.82 | 1215.69 | 1559.09 | 1864.76 | 2135.05 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-05-11
NDI - National Disability Insurance Agency | Other | Anil Kinagi |  | Contractor-Service Designer/UI/UX-Mid | 123 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Systems Integration & Build | 0 | 865.2 | 1121.6 | 1330.71 | 1645.42 | 2026.97 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-05-18
NEM - National Emergency Management Agency | Growth | Aleksandar Vranesevic |  | Contractor-Service Designer/UI/UX-Senior | 150 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Porting/Software Configuration | 0 | 0 | 1121.6 | 1330.71 | 1645.42 | 2026.97 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-05-25
NFS - National Film and Sound Archive of Australia | Growth | Aleksandar Vranesevic |  | Contractor-Tester-Lead | 150 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Hardware Design | 0 | 0 | 0 | 1209.81 | 1543.43 | 1878.47 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-06-01 | 20%
NGA - National Gallery of Australia | Other | Anil Kinagi |  | Contractor-Tester-Manager | 161 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Systems Installation / Decommissioning | 694.6 | 836.31 | 1011.14 | 1269.36 | 1505.97 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-06-08 | 20%
NHF - National Health Funding Body | Growth | Aleksandar Vranesevic |  | Contractor-Tester-Mid | 107 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Availability Management | 0 | 0 | 0 | 1556.32 | 1786.32 | 2118.69 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-06-15
NHM - National Health and Medical Research Council | Growth | Aleksandar Vranesevic |  | Contractor-Tester-Senior | 129 | 0 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | Service Lead Management | 0 | 1028.03 | 1196.98 | 1455.77 | 1674.78 | 1972.3 | 2371.47 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-06-22
NIA - National Indigenous Australians Agency​ | Growth | Aleksandar Vranesevic |  | Courtney Barnes | 157.28 | 0 | 45992 | 46080 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Service Acceptance | 0 | 0 | 0 | 1405.23 | 1550.27 | 1856.68 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-06-29
NLA - National Library of Australia | Growth | Aleksandar Vranesevic |  | Daniel Harris | 185.89 | 0 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Configuration Management | 0 | 1049.45 | 1217.29 | 1437.45 | 1602.45 | 1825.27 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-07-06
NMA - National Musuem of Australia | Growth | Aleksandar Vranesevic |  | Darren Krause | 161 | 0 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Asset Management | 0 | 964.77 | 1182.96 | 1611.86 | 1877.39 | 2309.75 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-07-13
NMI - National Measurement Institute | Growth | Aleksandar Vranesevic |  | David Smith | 162.5 | 0 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Change Management | 0 | 1295.95 | 1481.4 | 1839.58 | 2142.71 | 2534.91 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-07-20
NOP - National Offshore Petroleum Safety and Environmental Management Authority | Growth | Aleksandar Vranesevic |  | Deepak Kumar Mandya | 123 | 0 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Release & Deployment | 0 | 0 | 1089.39 | 1530.41 | 1927.22 | 2455.8 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-07-27
NPA - National Parks | Growth | Aleksandar Vranesevic |  | Deependra Singh | 129 | DM4 | [5 empty] | Defence - ICT Provider Arrangement (ICTPA) | System Software | 0 | 0 | 947.97 | 1281.16 | 1830.8 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-08-03
NQS - NDIS Quality and Safeguards Commission | Other | Anil Kinagi |  | Eddie Harris | 112.5 | EN3 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Capacity Management | 0 | 0 | 0 | 1542.39 | 1859.87 | 2259.69 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-08-10
NSW - NSW Government | Growth | Aleksandar Vranesevic |  | Elena Bimbilovski | 0 | MA4 |  |  | CAS |  |  | Defence - ICT Provider Arrangement (ICTPA) | Security Administration | 902.69 | 1010.57 | 1145.51 | 1320.24 | 1663.92 | 1965.31 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-08-17
OAI - Office of the Australian Information Commissioner | Growth | Aleksandar Vranesevic |  | Faran Muzaffar | 139 | 0 | 45474 | 45548 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Penetration Testing | 0 | 0 | 0 | 1177.67 | 1402.19 | 1868.14 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-08-24
OCO - Office of Commonwealth Ombudsman | Growth | Aleksandar Vranesevic |  | Gaurav Raghav | 181.65 | 0 | 45796 | 46073 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Radio Frequency Engineering | 0 | 901.47 | 1047.41 | 1364.29 | 1553.05 | 1889.04 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-08-31
ONA - Office of National Assessments | Growth | Aleksandar Vranesevic |  | Giribabu Paruchuri | 167 | 0 | 45677 | 46203 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Application Support | 0 | 919.24 | 1094.25 | 1345.14 | 1586.99 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-09-07
ONI - Office of National Intelligence | Growth | Aleksandar Vranesevic |  | Hadas Yehezkel | 198 | EN6 | 45922 |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | IT Infrastructure | 980.25 | 1130.46 | 1314.48 | 1553.77 | 0 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-09-14
OPC - Office of Parliamentary Counsel | Growth | Aleksandar Vranesevic |  | Haider Raza | 200 | EN4 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Database Administration | 0 | 911.1 | 1117.49 | 1388.45 | 1821.52 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-09-21
OPH - Old Parliament House | Growth | Aleksandar Vranesevic |  | Hanan Asghar | 164.2819 | 0 | 45474 | 46203 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Storage Management | 0 | 0 | 1331.89 | 1559.49 | 1779.41 | 2268.77 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-09-28
PAR - Parbery Consulting | Growth | Scott Foley |  | Harkulwant Singh | 144.47 | 0 | 45945 | 46203 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Network Support | 0 | 696.91 | 852.15 | 1058.92 | 1292.58 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-10-05 | 20%
PMC - Department of the Prime Minister and Cabinet | Growth | Aleksandar Vranesevic |  | Harrison Riepon | 136.24 | 0 | 45922 | 46112 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Problem Management | 0 | 0 | 1321.76 | 1543.97 | 1675.45 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-10-12
PSR - Professional Services Review Scheme | Growth | Aleksandar Vranesevic |  | Himanshu Mohan | 193 | 0 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Incident Management | 0 | 844.64 | 1070.37 | 1264.53 | 1544.87 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-10-19
QLD - Queensland Government | Growth | Scott Foley |  | Hisham Saber | 193.98 | 0 | 45978 | 46080 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Facilities Management | 0 | 0 | 1291.85 | 1509.45 | 1707.33 | 2247.37 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-10-26
RBA - Reserve Bank of Australia | Growth | Aleksandar Vranesevic |  | Husain Syed | 134 | 0 | 45420 | 46149 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Learning & Development Management | 0 | 0 | 1300.73 | 1530.73 | 1745.8 | 2132.73 | 2471.14 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-11-02
SAG - South Australia Government | Growth | Alex Kocz |  | Ian Hepples | 245 | DM6 | 45936 |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Competency Assessment | 0 | 0 | 1298.87 | 1533.48 | 1723.49 | 2103.03 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-11-09
SAP - SAP | Growth | Scott Foley |  | Ilyas Wajid | 0 | OP4 |  |  | OPS |  |  | Defence - ICT Provider Arrangement (ICTPA) | Learning, Design & Development | 0 | 0 | 1272.96 | 1538.84 | 1745.8 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-11-16
SAU - Services Australia | SAU | Aleksandar Vranesevic |  | Imran Saeed | 146 | CO5 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Learning Delivery | 0 | 0 | 1529.01 | 1770.76 | 2166.43 | 0 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-11-23
SFO - Salesforce | Growth | Scott Foley |  | Indraneel Dhavala | 124 | 0 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Teaching & Subject Formation | 0 | 0 | 0 | 0 | 2125.06 | 2445.79 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-11-30
SHF - Sydney Harbour Federation Trust | Growth | Aleksandar Vranesevic |  | Intizar Hassan | 181.71 | 0 | 45978 | 46063 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Performance Management | 0 | 0 | 0 | 1532.63 | 1726.64 | 2238.82 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-12-07
SIA - Sport Integrity Australia | Growth | Aleksandar Vranesevic |  | Jayprakash Hegde | 204.35 | 0 | 45957 |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Resourcing | 0 | 0 | 0 | 1606.46 | 1813.41 | 205.73 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-12-14
SNO - ServiceNow | Growth | Scott Foley |  | Jeffrey Wilkinson | 177 | 0 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Professional Development | 0 | 0 | 0 | 1414.17 | 1590.46 | 1934.55 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-12-21 | 100%
SYP - SYPAQ | Growth | William Scheer |  | Jinghan Zhang | 0 | OP4 |  |  | OPS |  |  | Defence - ICT Provider Arrangement (ICTPA) | Quality Mnagement | 0 | 0 | 1198.92 | 1423.56 | 1607.84 | 1945.39 | 2350.29 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2026-12-28 | 100%
TAL - Talent International | Growth | Siddhartha Sengupta |  | Joelle Blake | 245 | DM6 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Quality Assurance | 0 | 0 | 1198.23 | 1405.23 | 1550.27 | 1856.68 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2027-01-04
TEC - TechnologyOne | Growth | Scott Foley |  | Josh Wright | 190.63 | 0 | 45950 | 46066 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Measurement | 0 | 0 | 1199.33 | 1424.87 | 1541.43 | 1796.3 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2027-01-11
TEM - TechMahindra | Growth | Scott Foley |  | Junaid Ahmed | 100 | 0 | 45630 | 45930 | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Conformance Review | 0 | 0 | 1354.81 | 1603.19 | 1733.57 | 2069.46 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2027-01-18
TEQ - Tertiary Education Quality and Standards Agency | Growth | Aleksandar Vranesevic |  | Kanishk Mallick | 161 | 0 |  |  | CSD |  |  | Defence - ICT Provider Arrangement (ICTPA) | Safety Assessment | 0 | 0 | 0 | 0 | 1746.93 | 2103.19 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2027-01-25 | 20%
TSY - Department of the Treasury | Growth | Aleksandar Vranesevic |  | Karan Kella | 186.99 | 0 | 45474 | 46203 | CSD | 25/6: Gross cost updated for 1 July 2025 |  | Defence - ICT Provider Arrangement (ICTPA) | Digital Forensics | 0 | 0 | 0 | 1220.47 | 1466.42 | 1886.88 | 0 | [5 empty] | SFIA Level 1 | SFIA Level 2 | SFIA Level 3 | SFIA Level 4 | SFIA Level 5 | SFIA Level 6 | SFIA Level 7 | [5 empty] | 2027-02-01
UPT - Uptec | Growth | Aleksandar Vranesevic |  | Karthik Shivashankar | 146.76 | 0 |  |  | CSD |  |  | Boston Consulting Group (BCG) - teaming rates | Standard | 1700 | 1700 | 2000 | 2320 | 2720 | 4000 | [6 empty] | Consultant | Senior Consultant | Manager | Senior Manager | Director | Partner | [6 empty] | 2027-02-08
VAU - Vault Cloud | Growth | William Scheer |  | Keerthana Senthilkumar | 65.91 | 0 | 45926 | 46069 | CSD |  |  | Infosys - teaming rates | Digital | 0 | 0 | 1657.92 | 1761.52 | 2072.4 | 2072.4 | [6 empty] | Consultant | Senior Consultant | Manager | Senior Manager | Director | Partner | [6 empty] | 2027-02-15
VIC - Victoria Government | Growth | Alex Kocz |  | Kev Alexander | 154.94 | 0 | 45670 | 46015 | CSD |  |  | Infosys - teaming rates | Business | 0 | 0 | 1657.92 | 1761.52 | 2072.4 | 2072.4 | [6 empty] | Consultant | Senior Consultant | Manager | Senior Manager | Director | Partner | [6 empty] | 2027-02-22
WAG - Western Australian Government | Growth | Alex Kocz |  | Kevin Ho | 0 | OP7 |  |  | OPS |  |  | Tech Mahindra - teaming rates | Managed Service / Digital | 0 | 0 | 0 | 1976 | 2720 | 0 | [6 empty] | Consultant | Senior Consultant | Manager | Senior Manager | Director | Partner | [6 empty] | 2027-03-01
WGE - Workplace Gender Equality Agency | Growth | Aleksandar Vranesevic |  | Kevin Stephens | 171.36 | 0 | 45888 | 46010 | CSD |  |  | Lab3 x AFMA DM-26175 micropanel - teaming rates | Application Development Services | 1570 | 1680 | 1990 | [9 empty] | Intermediate | Senior | Principal | [9 empty] | 2027-03-08 | 20%
WOR - Workday | Growth | Scott Foley |  | Kosta Walker-Laskos | 151 | EN5 | 46083 |  | CSD |  |  | Lab3 x AFMA DM-26175 micropanel - teaming rates | Solution Design/Enterprise Architect Services | 1820 | 1888 | 2192 | [9 empty] | Intermediate | Senior | Principal | [9 empty] | 2027-03-15
|  |  |  | Kristina Coyne | 139 | 0 |  |  | CSD |  |  | Lab3 x AFMA DM-26175 micropanel - teaming rates | Systems Testing Services | 1256 | 1500 | 1710 | [9 empty] | Intermediate | Senior | Principal | [9 empty] | 2027-03-22 | 20%
|  |  |  | Lacy Pejcinovic | 146 | CO5 | 45887 |  | CSD |  |  | Lab3 x AFMA DM-26175 micropanel - teaming rates | Business Analysis Services | 1570 | 1680 | 2070 | [9 empty] | Intermediate | Senior | Principal | [9 empty] | 2027-03-29 | 20%
|  |  |  | Lindemour Vicencio | 90 | EN3 | 45957 |  | CSD |  |  | Lab3 x AFMA DM-26175 micropanel - teaming rates | Commercial Contract and Procurement Services | 1570 | 1680 | 2070 | [9 empty] | Intermediate | Senior | Principal | [9 empty] | 2027-04-05
|  |  |  | Lino Schildenfeld | 175 | 0 | 45988 | 46066 | CSD |  |  | Lab3 x AFMA DM-26175 micropanel - teaming rates | Cost Modelling | 1570 | 1680 | 2070 | [9 empty] | Intermediate | Senior | Principal | [9 empty] | 2027-04-12
|  |  |  | Lynne Hunt | 0 | OP2 |  |  | CAS |  |  | Alex Kocz - Custom Rates | Digital | 1400 | 1700 | 1900 | 2100 | 2100 | [7 empty] | Junior | Intermediate - Low | Intermediate - High | Senior | Expert | [7 empty] | 2027-04-19
|  |  |  | Lynne Sutherland | 90 | CO3 |  |  | CSD |  |  | Alex Kocz - Custom Rates | Business | 1400 | 1700 | 1900 | 2100 | 2100 | [7 empty] | Junior | Intermediate - Low | Intermediate - High | Senior | Expert | [7 empty] | 2027-04-26 | 20%
|  |  |  | Madhavi Pothunuru | 144.06 | 0 | 45957 | 46112 | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Application, software engineering and development services | 1520 | 1800 | 2200 | 3200 | 4000 | 5400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-05-03 |  |  | Maximum Rates - Application, software engineering and development services
|  |  |  | Mahesh Vemegal | 170.96 | 0 | 46083 |  | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Architecture services | 1520 | 1800 | 2200 | 3200 | 4000 | 5400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-05-10 |  |  | Maximum Rates - Architecture services
|  |  |  | Mark Volpato | 0 | PS6 |  |  | CAS |  |  | Digital Marketplace 2 | Maximum Rates - Business, systems and process analysis services | 1520 | 1800 | 2200 | 3200 | 4000 | 5400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-05-17 |  |  | Maximum Rates - Business, systems and process analysis services
|  |  |  | Meenal Kaul | 174 | CO5 | 45579 | 46295 | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Content and publishing services | 1200 | 1520 | 1800 | 2200 | 3200 | 4400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-05-24 |  |  | Maximum Rates - Content and publishing services
|  |  |  | Mehran Muzaffar | 138.91 | 0 | 45859 | 46003 | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Cybersecurity Services | 1520 | 1800 | 2200 | 3200 | 4000 | 5400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-05-31 | 20% |  | Maximum Rates - Cybersecurity Services
|  |  |  | Michael Castleman | 193 | 0 |  |  | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Data analytics and business intelligence services | 1520 | 1800 | 2200 | 3200 | 4000 | 5400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-06-07 |  |  | Maximum Rates - Data analytics and business intelligence services
|  |  |  | Michelle Chant | 146 | CO5 |  |  | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Digital sourcing, procurement and contract management services | 1520 | 1800 | 2200 | 3200 | 4000 | 5400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-06-14 | 20% |  | Maximum Rates - Digital sourcing, procurement and contract management services
|  |  |  | Miles Johnson | 90 | EN3 | 45950 |  | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Market research and advisory services | 1520 | 1800 | 2200 | 3200 | 4000 | 5400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-06-21 |  |  | Maximum Rates - Market research and advisory services
|  |  |  | Mir Atif Ali | 147 | 0 |  |  | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Marketing, advertising communications and engagement services | 1520 | 1800 | 2200 | 3200 | 4000 | 5400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-06-28 |  |  | Maximum Rates - Marketing, advertising communications and engagement services
|  |  |  | Mona Khimani | 145 | 0 | 45888 | 45924 | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Program, project and change management services | 1520 | 1800 | 2200 | 3200 | 4000 | 5400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-07-05 |  |  | Maximum Rates - Program, project and change management services
|  |  |  | Nadh Yandamuri | 187 | 0 | 45658 | 46387 | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Risk management, benchmarking and audit services | 1520 | 1800 | 2200 | 3200 | 4000 | 5400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-07-12 |  |  | Maximum Rates - Risk management, benchmarking and audit services
|  |  |  | Naomi Andrae | 146 | CO5 | 8/12/205 |  | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Solutions implementation services | 1520 | 1800 | 2200 | 3200 | 4000 | 5400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-07-19 |  |  | Maximum Rates - Solutions implementation services
|  |  |  | Nathan Richards | 146 | CO5 |  |  | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Strategy, policy and governance services | 1520 | 1800 | 2200 | 3200 | 4000 | 5400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-07-26 |  |  | Maximum Rates - Strategy, policy and governance services
|  |  |  | Navdeep Singh | 161.2331 | 0 | 45901 | 46066 | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Support and operations services | 1200 | 1520 | 1800 | 2200 | 3200 | 4400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-08-02 |  |  | Maximum Rates - Support and operations services
|  |  |  | Naveen Renukuntla | 214 | 0 | 45474 | 45905 | CSD |  |  | Digital Marketplace 2 | Maximum Rates - Training, learning and development services | 1200 | 1520 | 1800 | 2200 | 3200 | 4400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-08-09 |  |  | Maximum Rates - Training, learning and development services
|  |  |  | Naveen Roy | 144.17 | 0 | 45901 | 45994 | CSD |  |  | Digital Marketplace 2 | Maximum Rates - User research and design services | 1200 | 1520 | 1800 | 2200 | 3200 | 4400 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-08-16 |  |  | Maximum Rates - User research and design services
|  |  |  | Nisar Khan | 171.36 | 0 |  |  | CSD |  |  | Digital Marketplace 2 | Market Rates - Application, software engineering and development services | 1320 | 1520 | 1960 | 2440 | 3160 | 3960 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-08-23 |  |  | Market Rates - Application, software engineering and development services
|  |  |  | Paul Clark | 151 | EN5 | 46062 |  | CSD |  |  | Digital Marketplace 2 | Market Rates - Architecture services | 1320 | 1520 | 1960 | 2440 | 3160 | 3960 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-08-30 |  |  | Market Rates - Architecture services
|  |  |  | Perm-Consultant | 78 | CO2 | [5 empty] | Digital Marketplace 2 | Market Rates - Business, systems and process analysis services | 1320 | 1520 | 1960 | 2440 | 3160 | 3960 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-09-06 |  |  | Market Rates - Business, systems and process analysis services
|  |  |  | Perm-Consulting Partner | 248 | CO7 | [5 empty] | Digital Marketplace 2 | Market Rates - Content and publishing services | 1000 | 1320 | 1520 | 1960 | 2440 | 3160 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-09-13 |  |  | Market Rates - Content and publishing services
|  |  |  | Perm-Delivery Director | 245 | DM6 | [5 empty] | Digital Marketplace 2 | Market Rates - Cybersecurity Services | 1320 | 1520 | 1960 | 2440 | 3160 | 3960 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-09-20 |  |  | Market Rates - Cybersecurity Services
|  |  |  | Perm-Delivery Manager | 129 | DM4 | [5 empty] | Digital Marketplace 2 | Market Rates - Data analytics and business intelligence services | 1320 | 1520 | 1960 | 2440 | 3160 | 3960 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-09-27 |  |  | Market Rates - Data analytics and business intelligence services
|  |  |  | Perm-Delivery Partner | 248 | DM7 | [5 empty] | Digital Marketplace 2 | Market Rates - Digital sourcing, procurement and contract management services | 1320 | 1520 | 1960 | 2440 | 3160 | 3960 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-10-04 | 20% |  | Market Rates - Digital sourcing, procurement and contract management services
|  |  |  | Perm-Director | 189 | CO6 | [5 empty] | Digital Marketplace 2 | Market Rates - Market research and advisory services | 1320 | 1520 | 1960 | 2440 | 3160 | 3960 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-10-11 |  |  | Market Rates - Market research and advisory services
|  |  |  | Perm-Engineer | 90 | EN3 | [5 empty] | Digital Marketplace 2 | Market Rates - Marketing, advertising communications and engagement services | 1320 | 1520 | 1960 | 2440 | 3160 | 3960 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-10-18 |  |  | Market Rates - Marketing, advertising communications and engagement services
|  |  |  | Perm-Junior Engineer | 78 | EN2 | [5 empty] | Digital Marketplace 2 | Market Rates - Program, project and change management services | 1320 | 1520 | 1960 | 2440 | 3160 | 3960 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-10-25 |  |  | Market Rates - Program, project and change management services
|  |  |  | Perm-Lead Engineer | 151 | EN5 | [5 empty] | Digital Marketplace 2 | Market Rates - Risk management, benchmarking and audit services | 1320 | 1520 | 1960 | 2440 | 3160 | 3960 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-11-01 |  |  | Market Rates - Risk management, benchmarking and audit services
|  |  |  | Perm-Manager | 108 | CO4 | [5 empty] | Digital Marketplace 2 | Market Rates - Solutions implementation services | 1320 | 1520 | 1960 | 2440 | 3160 | 3960 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-11-08 |  |  | Market Rates - Solutions implementation services
|  |  |  | Perm-Principal Engineer | 198 | EN6 | [5 empty] | Digital Marketplace 2 | Market Rates - Strategy, policy and governance services | 1320 | 1520 | 1960 | 2440 | 3160 | 3960 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-11-15 |  |  | Market Rates - Strategy, policy and governance services
|  |  |  | Perm-Project Administrator | 57 | DM2 | [5 empty] | Digital Marketplace 2 | Market Rates - Support and operations services | 1000 | 1320 | 1520 | 1960 | 2440 | 3160 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-11-22 |  |  | Market Rates - Support and operations services
|  |  |  | Perm-Project Officer | 82 | DM3 | [5 empty] | Digital Marketplace 2 | Market Rates - Training, learning and development services | 1000 | 1320 | 1520 | 1960 | 2440 | 3160 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-11-29 |  |  | Market Rates - Training, learning and development services
|  |  |  | Perm-Snr Consultant | 90 | CO3 | [5 empty] | Digital Marketplace 2 | Market Rates - User research and design services | 1000 | 1320 | 1520 | 1960 | 2440 | 3160 | [6 empty] | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | [6 empty] | 2027-12-06 |  |  | Market Rates - User research and design services
|  |  |  | Perm-Snr Delivery Manager | 175 | DM5 | [5 empty] | DAFF STEPS - Advisory micropanel | Advisory < 3 months | 1480 | 1680 | 1960 | 2240 | 2600 | 3800 | [6 empty] | Consultant | Senior Consultant | Manager | Senior Manager | Principal | Partner | [6 empty] | 2027-12-13
|  |  |  | Perm-Snr Engineer | 108 | EN4 | [5 empty] | DAFF STEPS - Advisory micropanel | Advisory > 3 months | 1400 | 1600 | 1800 | 2100 | 2400 | 3200 | [6 empty] | Consultant | Senior Consultant | Manager | Senior Manager | Principal | Partner | [6 empty] | 2027-12-20 | 100%
|  |  |  | Perm-Snr Manager | 146 | CO5 | [5 empty] | DAFF DBD DM-26233 - Contractor micropanel | Developers | 1200 | 1450 | 1575 | 1700 | [8 empty] | Foundation SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2027-12-27 | 100%
|  |  |  | Phani Gollamudi | 198 | EN6 |  |  | CSD |  |  | DAFF DBD DM-26233 - Contractor micropanel | Service Designers | 1400 | 1500 | 1600 | 1700 | [8 empty] | Foundation SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-01-03
|  |  |  | Pip Naka | 126.89 | 0 | 45783 | 45838 | CSD |  |  | DAFF DBD DM-26233 - Contractor micropanel | Interaction Designers | 1250 | 1400 | 1550 | 1700 | [8 empty] | Foundation SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-01-10
|  |  |  | Praveena Akuthota | 120 | 0 |  |  | CSD |  |  | DAFF DBD DM-26233 - Contractor micropanel | Business Analysts | 1050 | 1300 | 1550 | 1800 | [8 empty] | Foundation SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-01-17
|  |  |  | Raheem Baig | 126.59 | 0 | 45670 | 46393 | CSD |  |  | DAFF DBD DM-26233 - Contractor micropanel | User Researchers | 1275 | 1350 | 1425 | 1500 | [8 empty] | Foundation SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-01-24 | 20%
|  |  |  | Rajasekhara Lankela | 173.64 | 0 |  |  | CSD |  |  | DAFF DBD DM-26233 - Contractor micropanel | Delivery Managers | 1050 | 1440 | 1920 | 2400 | [8 empty] | Foundation SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-01-31
|  |  |  | Rakesh Bommineni | 161 | 0 |  |  | CSD |  |  | DAFF DBD DM-26233 - Contractor micropanel | Product Managers | 1200 | 1470 | 1835 | 2200 | [8 empty] | Foundation SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-02-07
|  |  |  | Rakkhi Joy | 157.28 | 0 | 45888 | 46003 | CSD |  |  | DAFF DBD DM-26233 - Contractor micropanel | Technical Leads | 1150 | 1500 | 1850 | 2200 | [8 empty] | Foundation SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-02-14
|  |  |  | Ram Paramasamy | 170.96 | 0 | 45831 | 45887 | CSD |  |  | DAFF DBD DM-26233 - Contractor micropanel | Testers | 800 | 1100 | 1200 | 1300 | [8 empty] | Foundation SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-02-21
|  |  |  | Ranganath Barthur | 170.39 | 0 | 45888 | 46038 | CSD |  |  | DAFF DBD DM-26233 - Contractor micropanel | Techncial Architects | 1450 | 1700 | 1950 | 2200 | [8 empty] | Foundation SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-02-28
|  |  |  | Ravi Singh | 193 | 0 |  |  | CSD |  |  | DAFF DBD DM-26233 - Contractor micropanel | Change Manager | 1300 | 1600 | 1900 | 2200 | [8 empty] | Foundation SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-03-06
|  |  |  | Rehan Asghar | 157.6037 | 0 | 45803 | 46038 | CSD |  |  | DAFF DBD DM-26233 - Contractor micropanel | Content Designer | 1025 | 1250 | 1475 | 1700 | [8 empty] | Foundation SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-03-13 | 40%
|  |  |  | Richard Ryan | 178 | DM5 |  |  | CSD |  |  | DOH SME Supplementary Teams Arrangement (STA) - micropanel | Digital Strategy | 1440 | 1760 | 2120 | 2960 | [8 empty] | Junior SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-03-20 | 20%
|  |  |  | Roshan Menon | 176.31 | 0 | [5 empty] | DOH SME Supplementary Teams Arrangement (STA) - micropanel | Enterprise Architecture | 1376 | 1720 | 2064 | 2864 | [8 empty] | Junior SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-03-27
|  |  |  | Saad Rashid | 161 | 0 |  |  | CSD |  |  | DOH SME Supplementary Teams Arrangement (STA) - micropanel | Solution Architecture | 1320 | 1600 | 1944 | 2744 | [8 empty] | Junior SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-04-03
|  |  |  | Sai Rakesh | 185.89 | 0 |  |  | CSD |  |  | DOH SME Supplementary Teams Arrangement (STA) - micropanel | Technical Leadership | 1264 | 1544 | 1832 | 2520 | [8 empty] | Junior SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-04-10
|  |  |  | Sam Muzaffar | 137.085 | 0 | 45880 | 46014 | CSD |  |  | DOH SME Supplementary Teams Arrangement (STA) - micropanel | Dev/SecOps | 1376 | 1720 | 2064 | 2744 | [8 empty] | Junior SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-04-17
|  |  |  | Samuel Penumaka | 189.66 | 0 |  |  | CSD |  |  | DOH SME Supplementary Teams Arrangement (STA) - micropanel | Functional Consultancy | 1144 | 1432 | 1720 | 2288 | [8 empty] | Junior SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-04-24 | 20%
|  |  |  | Sankar Kumar Chellam | 160.275 | 0 | 45985 | 46112 | CSD |  |  | DOH SME Supplementary Teams Arrangement (STA) - micropanel | Integration Surge Support | 1264 | 1600 | 1944 | 2520 | [8 empty] | Junior SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-05-01
|  |  |  | Sankari Kalaiselvan | 131.64 | 0 | 45523 | 46203 | CSD | 25/6: Base cost updated for 1 July 2025 |  | DOH SME Supplementary Teams Arrangement (STA) - micropanel | Cyber Surge Support | 1376 | 1720 | 2176 | 2864 | [8 empty] | Junior SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-05-08
|  |  |  | Satyendra Bhojendra | 170.96 | 0 | 45994 | 46080 | CSD |  |  | DOH SME Supplementary Teams Arrangement (STA) - micropanel | Data Architecture | 1376 | 1720 | 2064 | 2632 | [8 empty] | Junior SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-05-15
|  |  |  | Sazzad Khandakar | 203.02 |  |  |  | CSD |  |  | DOH SME Supplementary Teams Arrangement (STA) - micropanel | Project/Product/Delivery Management | 1264 | 1544 | 1832 | 2400 | [8 empty] | Junior SFIA Level 4 | Intermediate SFIA Level 5 | Senior SFIA Level 6 | Expert SFIA Level 7 | [8 empty] | 2028-05-22
|  |  |  | Scott Foley | 0 | BD7 | 45733 |  | CAS |  |  | SAP Professional Services Standing Offer Arrangement | SAP Solution Technical Architect | 1600 | 1900 | 2100 | [9 empty] | Essentials (1-3yrs) | Advanced (4-7yrs) | Expert (8yrs+) | [9 empty] | 2028-05-29 | 20%
|  |  |  | Senthurvasan Ganeshwaran | 160.275 | 0 | 46055 | 46568 | CSD |  |  | SAP Professional Services Standing Offer Arrangement | SAP Functional Domain Architect | 1600 | 1900 | 2100 | [9 empty] | Essentials (1-3yrs) | Advanced (4-7yrs) | Expert (8yrs+) | [9 empty] | 2028-06-05
|  |  |  | Sheelesh Kumar | 197.01 | 0 | 45474 | 46203 | CSD | 25/6: Gross cost updated for 1 July 2025 |  | SAP Professional Services Standing Offer Arrangement | SAP Developer | 1500 | 1800 | 2000 | [9 empty] | Essentials (1-3yrs) | Advanced (4-7yrs) | Expert (8yrs+) | [9 empty] | 2028-06-12 | 20%
|  |  |  | Shefali Middha | 174 | 0 | 45628 | 46326 | CSD |  |  | SAP Professional Services Standing Offer Arrangement | SAP Functional Consultant | 1500 | 1800 | 2000 | [9 empty] | Essentials (1-3yrs) | Advanced (4-7yrs) | Expert (8yrs+) | [9 empty] | 2028-06-19
|  |  |  | Sian Davies | 108 | CO4 |  |  | CSD |  |  | SAP Professional Services Standing Offer Arrangement | SAP Integration Specialist | 0 | 1800 | 2000 | [9 empty] | Essentials (1-3yrs) | Advanced (4-7yrs) | Expert (8yrs+) | [9 empty] | 2028-06-26
|  |  |  | Siddhartha Sengupta | 231 | EN6 |  |  | CSD |  |  | SAP Professional Services Standing Offer Arrangement | SAP Security Consultant | 0 | 1900 | 2100 | [9 empty] | Essentials (1-3yrs) | Advanced (4-7yrs) | Expert (8yrs+) | [9 empty] | 2028-07-03
|  |  |  | Sridhar Guda | 173.64 | 0 |  |  | CSD |  |  | SAP Professional Services Standing Offer Arrangement | SAP Project Manager | 1400 | 1600 | 1800 | [9 empty] | Essentials (1-3yrs) | Advanced (4-7yrs) | Expert (8yrs+) | [9 empty] | 2028-07-10
|  |  |  | Stacy Bosel | 146 | CO5 |  |  | CSD |  |  | SAP Professional Services Standing Offer Arrangement | SAP Software Tester | 1200 | 1400 | 1600 | [9 empty] | Essentials (1-3yrs) | Advanced (4-7yrs) | Expert (8yrs+) | [9 empty] | 2028-07-17
|  |  |  | Stephen Boulton | 133.2486 | 0 | 46069 | 46374 | CSD |  |  | SAP Professional Services Standing Offer Arrangement | SAP Basis Consultant | 0 | 1900 | 0 | [9 empty] | Essentials (1-3yrs) | Advanced (4-7yrs) | Expert (8yrs+) | [9 empty] | 2028-07-24
|  |  |  | Stephen Kamal | 150 | 0 | 45943 | 46080 | CSD |  |  | SAP Professional Services Standing Offer Arrangement | SAP Release Manager | 0 | 1600 | 0 | [9 empty] | Essentials (1-3yrs) | Advanced (4-7yrs) | Expert (8yrs+) | [9 empty] | 2028-07-31
|  |  |  | Stirling Butcher | 149.59 | 0 | 45888 | 45924 | CSD |  |  | Cloud Marketplace | AI Machine Learning | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Associate Consultant | Consultant | Senior Consultant | Managing Consultant | Principal Consultant | [7 empty] | 2028-08-07
|  |  |  | Sujith Sasankan Leela | 120.21 | 0 | 45978 | 46073 | CSD |  |  | Cloud Marketplace | Analytics Forecasting Reporting | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Associate Consultant | Consultant | Senior Consultant | Managing Consultant | Principal Consultant | [7 empty] | 2028-08-14
|  |  |  | Surya Ratakumtla | 90 | EN3 | 45895 | 46078 | CSD |  |  | Cloud Marketplace | App Integration Middleware | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Associate Consultant | Consultant | Senior Consultant | Managing Consultant | Principal Consultant | [7 empty] | 2028-08-21
|  |  |  | Swati Dhelia | 0 | PS4 |  |  | CAS |  |  | Cloud Marketplace | Corporate Applications | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Associate Consultant | Consultant | Senior Consultant | Managing Consultant | Principal Consultant | [7 empty] | 2028-08-28
|  |  |  | Swetha Komma | 128.22 | 0 | 45967 | 46111 | CSD |  |  | Cloud Marketplace | Customer Support Engagement | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Associate Consultant | Consultant | Senior Consultant | Managing Consultant | Principal Consultant | [7 empty] | 2028-09-04
|  |  |  | Tejas Joshi | 186.99 | 0 | 45474 | 46203 | CSD | 27/6: Base cost updated for 1 July 2025 |  | Cloud Marketplace | Data Migration Transformation | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Associate Consultant | Consultant | Senior Consultant | Managing Consultant | Principal Consultant | [7 empty] | 2028-09-11
|  |  |  | Tim Kreukniet | 146 | CO5 | 45894 |  | CSD |  |  | Cloud Marketplace | Data Warehousing | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Associate Consultant | Consultant | Senior Consultant | Managing Consultant | Principal Consultant | [7 empty] | 2028-09-18
|  |  |  | Vikas Jayaram | 176.3 | 0 | 45831 | 45887 | CSD |  |  | Cloud Marketplace | Database | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Associate Consultant | Consultant | Senior Consultant | Managing Consultant | Principal Consultant | [7 empty] | 2028-09-25
|  |  |  | Vinnie Tumukunta | 144.04 | 0 | 45670 | 46393 | CSD | Old cost rate of $149.59 till 6th Jan. New rate from 7th Jan 2026 |  | Cloud Marketplace | Developer Tools | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Associate Consultant | Consultant | Senior Consultant | Managing Consultant | Principal Consultant | [7 empty] | 2028-10-02 | 20%
|  |  |  | Vivek Shah | 183.49 | 0 | 45796 | 46073 | CSD |  |  | Cloud Marketplace | Edge Computing | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Associate Consultant | Consultant | Senior Consultant | Managing Consultant | Principal Consultant | [7 empty] | 2028-10-09
|  |  |  | William Scheer | 248 | CE7 |  |  | OPS |  |  | Cloud Marketplace | Risk Compliance | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Associate Consultant | Consultant | Senior Consultant | Managing Consultant | Principal Consultant | [7 empty] | 2028-10-16
|  |  |  | Witner Haway | 145 | 0 |  |  | CSD |  |  | Cloud Marketplace | Storage Backup Recovery | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Associate Consultant | Consultant | Senior Consultant | Managing Consultant | Principal Consultant | [7 empty] | 2028-10-23
|  |  |  | Yara Yangot | 90 | EN3 | 45978 |  | CSD |  |  | Cloud Marketplace | Virtualised Computing | 1320 | 1520 | 2200 | 3200 | 5360 | [7 empty] | Associate Consultant | Consultant | Senior Consultant | Managing Consultant | Principal Consultant | [7 empty] | 2028-10-30
|  |  |  | Zahid Khan | 137.62 | 0 | 45796 | 45954 | CSD | [28 empty] | 2028-11-06
|  |  |  | Zoe Haseler | 90 | CO3 | 45859 |  | CSD | [28 empty] | 2028-11-13
2028-11-20
2028-11-27
2028-12-04
2028-12-11
2028-12-18
[38 empty] | 2028-12-25 | 100%
[38 empty] | 2029-01-01 | 100%
2029-01-08
2029-01-15
[38 empty] | 2029-01-22 | 20%
2029-01-29
2029-02-05
2029-02-12
2029-02-19
2029-02-26
2029-03-05
[38 empty] | 2029-03-12 | 20%
2029-03-19
[38 empty] | 2029-03-26 | 20%
[38 empty] | 2029-04-02 | 20%
2029-04-09
2029-04-16
[38 empty] | 2029-04-23 | 20%
2029-04-30
2029-05-07
2029-05-14
2029-05-21
[38 empty] | 2029-05-28 | 20%
2029-06-04
[38 empty] | 2029-06-11 | 20%
2029-06-18
2029-06-25

## Time Plan (Multiple Release)
Forecast Date | 2026-03-02 | 887523.63 | 982529.6 | 933218.04 |  |  | 907273.5 | [8 empty] | -5.025% |  |  |  | 933218.04 |  |  | Monday Commencing (Select) | [32 empty] | Hypercare
Contract Start Date | 2026-02-09 | -5.025% | -5.149% | 45694.41 | [5 empty] | Delivery | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492 | 493 | 494 | 495 | 496 | 497 | 498 | 499 | 500 | 501 | 502 | 503 | 504 | 505 | 506 | 507 | 508 | 509 | 510 | 511 | 512 | 513 | 514 | 515 | 516 | 517 | 518 | 519 | 520 | 521 | 522 | 523 | 524 | 525 | 526 | 527 | 528 | 529 | 530 | 531 | 532 | 533 | 534 | 535 | 536 | 537 | 538 | 539 | 540 | 541 | 542 | 543 | 544 | 545 | 546 | 547 | 548 | 549 | 550 | 551 | 552 | 553 | 554 | 555 | 556 | 557 | 558 | 559 | 560 | 561 | 562 | 563 | 564 | 565 | 566 | 567 | 568 | 569 | 570 | 571 | 572 | 573 | 574 | 575 | 576 | 577 | 578 | 579 | 580 | 581 | 582 | 583 | 584 | 585 | 586 | 587 | 588 | 589 | 590 | 591
Milestone | Deliverable | Resource | Charge Out Level | Job Role | Panel Hourly Rate $ ex-GST | Discount (%) | Discounted Hourly Rate $ ex GST | Discounted Daily Rate $ ex-GST | Hourly Gross Cost $ | Budget Hours | Budget $ ex GST | Actual Hours as at 09-Feb | Charge $ ex GST | Balance $ ex GST (Budget - Charge) | Gross Cost $ ex GST | Gross Margin | Forecast hours | Forecast Days | Forecast $ ex GST | Forecast Gross Cost $ ex GST | Variance at completion (ex GST) | Variance at completion (%) | time axis 2026-02-09 to 2037-06-01
| Account Manager | Aleksandar Vranesevic | Panel | Digital Marketplace 2 | [18 empty] | 2026-03-09: 20%; 2026-03-30: 20%; 2026-04-06: 20%; 2026-04-20: 20%; 2026-06-01: 20%; 2026-06-08: 20%; 2026-10-05: 20%; 2026-12-21: 100%; 2026-12-28: 100%; 2027-01-25: 20%; 2027-03-08: 20%; 2027-03-22: 20%; 2027-03-29: 20%; 2027-04-26: 20%; 2027-05-31: 20%; 2027-06-14: 20%; 2027-10-04: 20%; 2027-12-20: 100%; 2027-12-27: 100%; 2028-01-24: 20%; 2028-03-13: 40%; 2028-03-20: 20%; 2028-04-24: 20%; 2028-05-29: 20%; 2028-06-12: 20%; 2028-10-02: 20%; 2028-12-25: 100%; 2029-01-01: 100%; 2029-01-22: 20%; 2029-03-12: 20%; 2029-03-26: 20%; 2029-04-02: 20%; 2029-04-23: 20%; 2029-05-28: 20%; 2029-06-11: 20%
| Engagement Manager | Hadas Yehezkel | Category | Market Rates - Solutions implementation services | [5 empty] | 0 | 0 | 716.25 | 112758.45 | -112758.45 | 116011.5 | -5.025% | 5832 | 729 | 933218.04 | 982529.6 | -1045976.49
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 | 120 | 24888 | -24888 | 29400 | -18.13% | 20 | 2.5 | 4148 | 4900 | -29036 |  | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 50%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Lacy Pejcinovic | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 | 144.5 | 21949.55 | -21949.55 | 21097 | 3.884% | 40 | 5 | 6076 | 5840 | -28025.55 |  | 2026-02-09: 170%; 2026-02-16: 110%; 2026-02-23: 70%; 2026-03-02: 100%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 | 120 | 18228 | -18228 | 10800 | 40.75% | 40 | 5 | 6076 | 3600 | -24304 |  | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 | 66 | 15642 | -15642 | 13068 | 16.46% | 30 | 3.75 | 7110 | 5940 | -22752 |  | 2026-02-09: 70%; 2026-02-16: 50%; 2026-02-23: 50%; 2026-03-02: 75%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Bradley Burge | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 151 |  | 0 |  | 0 | 0 | 0 | 27.19% | 20 | 2.5 | 4148 | 3020 | -4148 |  | 2026-02-23: 50%; 2026-03-02: 50%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 | 66.5 | 10101.35 | -10101.35 | 9709 | 3.884% | 8 | 1 | 1215.2 | 1168 | -11316.55 |  | 2026-02-09: 20%; 2026-02-16: 30%; 2026-02-23: 85%; 2026-03-02: 20%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 | 54.75 | 0 | 0 | 10840.5 | 100% | 20 | 2.5 | 0 | 3960 | 0 |  | 2026-02-09: 25%; 2026-02-16: 57%; 2026-02-23: 50%; 2026-03-02: 50%
M1 - Discovery Completion | 1.3 Detailed delivery plan, RACI of build/delivery meeting AGD Operating Model requirements | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M1 - Discovery Completion | 1.4 Acceptance certificate | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Contingency |  |  |  | 5% | 1438.66 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 2026-02-16: 2.5%
M2 - Sprint 1 and 2 completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 140 | 17.5 | 29036 | 34300 | -29036 |  | 2026-03-02: 50%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 | 40.75% | 120 | 15 | 18228 | 10800 | -18228 |  | 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.1 Project management and compliance documentation | Lacy Pejcinovic | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 | 144.5 | 21949.55 | -21949.55 | 21097 | 3.884% | 120 | 15 | 18228 | 17520 | -40177.55 |  | 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 | 16.46% | 40 | 5 | 9480 | 7920 | -9480 |  | 2026-03-02: 25%; 2026-03-09: 25%; 2026-03-16: 25%; 2026-03-23: 25%
M2 - Sprint 1 and 2 completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M2 - Sprint 1 and 2 completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 | 17.57% | 140 | 17.5 | 29036 | 23934.4 | -29036 |  | 2026-02-23: 25%; 2026-03-02: 50%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 160 | 20 | 0 | 31680 | 0 |  | 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -24304 |  | 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M2 - Sprint 1 and 2 completion | 2.2 Build | Contingency |  |  |  | 5% | 7928.4 |  | 0 |  | 0 |  | 0 | 0 | 0 | 100% | 1 | 0.125 | 7928.4 | 0 | -7928.4 |  | 2026-03-23: 2.5%
M3 - Sprint 3 and 4 completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 152 | 19 | 31524.8 | 37240 | -31524.8 |  | 2026-03-30: 80%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 | 40.75% | 160 | 20 | 24304 | 14400 | -24304 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 | 16.46% | 80 | 10 | 18960 | 15840 | -18960 |  | 2026-03-30: 50%; 2026-04-06: 50%; 2026-04-13: 50%; 2026-04-20: 50%
M3 - Sprint 3 and 4 completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 | 3.884% | 120 | 15 | 18228 | 17520 | -18228 |  | 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 | 17.57% | 160 | 20 | 33184 | 27353.6 | -33184 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 160 | 20 | 0 | 31680 | 0 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -24304 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 | -5.991% | 80 | 10 | 12152 | 12880 | -12152 |  | 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Contingency |  |  |  | 5% | 9645.64 |  | 0 |  | 0 |  | 0 | 0 | 0 | 100% | 1 | 0.125 | 9645.64 | 0 | -9645.64 |  | 2026-04-20: 2.5%
M4 - Sprint 5 and 6 completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 160 | 20 | 33184 | 39200 | -33184 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 | 40.75% | 160 | 20 | 24304 | 14400 | -24304 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 | 16.46% | 80 | 10 | 18960 | 15840 | -18960 |  | 2026-04-27: 50%; 2026-05-04: 50%; 2026-05-11: 50%; 2026-05-18: 50%
M4 - Sprint 5 and 6 completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 | 3.884% | 160 | 20 | 24304 | 23360 | -24304 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 | 17.57% | 160 | 20 | 33184 | 27353.6 | -33184 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 160 | 20 | 0 | 31680 | 0 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -24304 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 | -5.991% | 160 | 20 | 24304 | 25760 | -24304 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M5 - Test Completion & Go-live | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 160 | 20 | 33184 | 39200 | -33184 |  | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M5 - Test Completion & Go-live | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M5 - Test Completion & Go-live | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M5 - Test Completion & Go-live | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 | 3.884% | 160 | 20 | 24304 | 23360 | -24304 |  | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M5 - Test Completion & Go-live | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M5 - Test Completion & Go-live | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M5 - Test Completion & Go-live | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 80 | 10 | 0 | 15840 | 0 |  | 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%
M5 - Test Completion & Go-live | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 80 | 10 | 12152 | 12080 | -12152 |  | 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%
M5 - Test Completion & Go-live | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 | -5.991% | 160 | 20 | 24304 | 25760 | -24304 |  | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M6 - Hypercare completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 80 | 10 | 16592 | 19600 | -16592 |  | 2026-06-22: 50%; 2026-06-29: 50%; 2026-07-06: 50%; 2026-07-13: 50%
M6 - Hypercare completion | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 100%
M6 - Hypercare completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 40 | 5 | 0 | 7920 | 0 |  | 2026-06-22: 50%; 2026-06-29: 50%
M6 - Hypercare completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -24304 |  | 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 100%
M6 - Hypercare completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M7 - AI and Self-Service Portal | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 160 | 20 | 33184 | 39200 | -33184 |  | 2026-06-22: 50%; 2026-06-29: 50%; 2026-07-06: 50%; 2026-07-13: 50%; 2026-07-20: 50%; 2026-07-27: 50%; 2026-08-03: 50%; 2026-08-10: 50%
M7 - AI and Self-Service Portal | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 | 40.75% | 60 | 7.5 | 9114 | 5400 | -9114 |  | 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%
M7 - AI and Self-Service Portal | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | bar: 2026-05-25 to 2026-08-10
M7 - AI and Self-Service Portal | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | bar: 2026-05-25 to 2026-08-10
M7 - AI and Self-Service Portal | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | bar: 2026-05-25 to 2026-08-10
M7 - AI and Self-Service Portal | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-07-20: 100%; 2026-07-27: 100%; 2026-08-03: 100%; 2026-08-10: 100%
M7 - AI and Self-Service Portal | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 40 | 5 | 0 | 7920 | 0 |  | 2026-06-22: 50%; 2026-06-29: 50%
M7 - AI and Self-Service Portal | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 240 | 30 | 36456 | 36240 | -36456 |  | 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%; 2026-07-20: 100%; 2026-07-27: 100%; 2026-08-03: 100%; 2026-08-10: 100%
M7 - AI and Self-Service Portal | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 | -5.991% | 120 | 15 | 18228 | 19320 | -18228 |  | 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%
| RESOURCE LOADING | Anil Kinagi |  | Project Manager |  |  | 207.4 | [15 empty] | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 80%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 100%; 2026-07-20: 50%; 2026-07-27: 50%; 2026-08-03: 50%; 2026-08-10: 50%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Lacy Pejcinovic |  | Business Analyst |  |  | 151.9 | [15 empty] | 2026-02-09: 170%; 2026-02-16: 110%; 2026-02-23: 70%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 0%; 2026-04-06: 0%; 2026-04-13: 0%; 2026-04-20: 0%; 2026-04-27: 0%; 2026-05-04: 0%; 2026-05-11: 0%; 2026-05-18: 0%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Lynne Sutherland |  | Business Analyst |  |  | 151.9 | [15 empty] | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Hadas Yehezkel |  | ServiceNow Architect |  |  | 237 | [15 empty] | 2026-02-09: 70%; 2026-02-16: 50%; 2026-02-23: 50%; 2026-03-02: 100%; 2026-03-09: 25%; 2026-03-16: 25%; 2026-03-23: 25%; 2026-03-30: 50%; 2026-04-06: 50%; 2026-04-13: 50%; 2026-04-20: 50%; 2026-04-27: 50%; 2026-05-04: 50%; 2026-05-11: 50%; 2026-05-18: 50%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Bradley Burge |  | Lead ServiceNow Developer |  |  | 207.4 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 50%; 2026-03-02: 150%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 100%; 2026-07-20: 100%; 2026-07-27: 100%; 2026-08-03: 100%; 2026-08-10: 100%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Michelle Chant |  | Change Manager |  |  | 151.9 | [15 empty] | 2026-02-09: 20%; 2026-02-16: 30%; 2026-02-23: 85%; 2026-03-02: 20%; 2026-03-09: 0%; 2026-03-16: 0%; 2026-03-23: 0%; 2026-03-30: 0%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Phani Gollamudi |  | ServiceNow Developer |  |  | 0 | [15 empty] | 2026-02-09: 25%; 2026-02-16: 57%; 2026-02-23: 50%; 2026-03-02: 150%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%; 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Contingency |  | 0 |  |  | 1438.66 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 2.5%; 2026-02-23: 0%; 2026-03-02: 0%; 2026-03-09: 0%; 2026-03-16: 0%; 2026-03-23: 2.5%; 2026-03-30: 0%; 2026-04-06: 0%; 2026-04-13: 0%; 2026-04-20: 2.5%; 2026-04-27: 0%; 2026-05-04: 0%; 2026-05-11: 0%; 2026-05-18: 0%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Mahesh Vemegal |  | Lead ServiceNow Developer |  |  | 207.4 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 25%; 2026-03-02: 50%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Kosta Walker-Laskos |  | ServiceNow Developer |  |  | 151.9 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 0%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 100%; 2026-07-20: 100%; 2026-07-27: 100%; 2026-08-03: 100%; 2026-08-10: 100%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Contractor-Tester-Manager |  | Senior Tester |  |  | 151.9 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 0%; 2026-03-02: 0%; 2026-03-09: 0%; 2026-03-16: 0%; 2026-03-23: 0%; 2026-03-30: 0%; 2026-04-06: 0%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
Actuals | bar: 2026-02-09 to 2026-02-23

## Time Plan (Partial Phani)
Forecast Date | 2026-03-02 | 887523.63 | 764069.6 | -887528.89 |  |  | 907273.5 | [8 empty] | 0.8392% | [6 empty] | Monday Commencing (Select) | [32 empty] | Hypercare
Contract Start Date | 2026-02-09 | 0.8392% | [7 empty] | Delivery | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492 | 493 | 494 | 495 | 496 | 497 | 498 | 499 | 500 | 501 | 502 | 503 | 504 | 505 | 506 | 507 | 508 | 509 | 510 | 511 | 512 | 513 | 514 | 515 | 516 | 517 | 518 | 519 | 520 | 521 | 522 | 523 | 524 | 525 | 526 | 527 | 528 | 529 | 530 | 531 | 532 | 533 | 534 | 535 | 536 | 537 | 538 | 539 | 540 | 541 | 542 | 543 | 544 | 545 | 546 | 547 | 548 | 549 | 550 | 551 | 552 | 553 | 554 | 555 | 556 | 557 | 558 | 559 | 560 | 561 | 562 | 563 | 564 | 565 | 566 | 567 | 568 | 569 | 570 | 571 | 572 | 573 | 574 | 575 | 576 | 577 | 578 | 579 | 580 | 581 | 582 | 583 | 584 | 585 | 586 | 587 | 588 | 589 | 590 | 591
Milestone | Deliverable | Resource | Charge Out Level | Job Role | Panel Hourly Rate $ ex-GST | Discount (%) | Discounted Hourly Rate $ ex GST | Discounted Daily Rate $ ex-GST | Hourly Gross Cost $ | Budget Hours | Budget $ ex GST | Actual Hours as at 09-Feb | Charge $ ex GST | Balance $ ex GST (Budget - Charge) | Gross Cost $ ex GST | Gross Margin | Forecast hours | Forecast Days | Forecast $ ex GST | Forecast Gross Cost $ ex GST | Variance at completion (ex GST) | Variance at completion (%) | time axis 2026-02-09 to 2037-06-01
| Account Manager | Aleksandar Vranesevic | Panel | Digital Marketplace 2 | [18 empty] | 2026-03-09: 20%; 2026-03-30: 20%; 2026-04-06: 20%; 2026-04-20: 20%; 2026-06-01: 20%; 2026-06-08: 20%; 2026-10-05: 20%; 2026-12-21: 100%; 2026-12-28: 100%; 2027-01-25: 20%; 2027-03-08: 20%; 2027-03-22: 20%; 2027-03-29: 20%; 2027-04-26: 20%; 2027-05-31: 20%; 2027-06-14: 20%; 2027-10-04: 20%; 2027-12-20: 100%; 2027-12-27: 100%; 2028-01-24: 20%; 2028-03-13: 40%; 2028-03-20: 20%; 2028-04-24: 20%; 2028-05-29: 20%; 2028-06-12: 20%; 2028-10-02: 20%; 2028-12-25: 100%; 2029-01-01: 100%; 2029-01-22: 20%; 2029-03-12: 20%; 2029-03-26: 20%; 2029-04-02: 20%; 2029-04-23: 20%; 2029-05-28: 20%; 2029-06-11: 20%
| Engagement Manager | Hadas Yehezkel | Category | Market Rates - Solutions implementation services | [5 empty] | 0 | 0 | 716.25 | 112758.45 | -112758.45 | 116011.5 | 0.8392% | 4569 | 571.125 | 774770.44 | 764069.6 | -887528.89
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 | 120 | 24888 | -24888 | 29400 | -18.13% | 20 | 2.5 | 4148 | 4900 | -29036 |  | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 50%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Lacy Pejcinovic | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 | 144.5 | 21949.55 | -21949.55 | 21097 | 3.884% | 40 | 5 | 6076 | 5840 | -28025.55 |  | 2026-02-09: 170%; 2026-02-16: 110%; 2026-02-23: 70%; 2026-03-02: 100%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 | 120 | 18228 | -18228 | 10800 | 40.75% | 40 | 5 | 6076 | 3600 | -24304 |  | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 | 66 | 15642 | -15642 | 13068 | 16.46% | 30 | 3.75 | 7110 | 5940 | -22752 |  | 2026-02-09: 70%; 2026-02-16: 50%; 2026-02-23: 50%; 2026-03-02: 75%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Bradley Burge | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 151 |  | 0 |  | 0 | 0 | 0 | 27.19% | 20 | 2.5 | 4148 | 3020 | -4148 |  | 2026-02-23: 50%; 2026-03-02: 50%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 | 66.5 | 10101.35 | -10101.35 | 9709 | 3.884% | 8 | 1 | 1215.2 | 1168 | -11316.55 |  | 2026-02-09: 20%; 2026-02-16: 30%; 2026-02-23: 85%; 2026-03-02: 20%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 | 54.75 | 0 | 0 | 10840.5 | 100% | 20 | 2.5 | 0 | 3960 | 0 |  | 2026-02-09: 25%; 2026-02-16: 57%; 2026-02-23: 50%; 2026-03-02: 50%
M1 - Discovery Completion | 1.3 Detailed delivery plan, RACI of build/delivery meeting AGD Operating Model requirements | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M1 - Discovery Completion | 1.4 Acceptance certificate | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Contingency |  |  |  | 5% | 1438.66 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 2026-02-16: 2.5%
M2 - Sprint 1 and 2 completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 140 | 17.5 | 29036 | 34300 | -29036 |  | 2026-03-02: 50%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 | 40.75% | 120 | 15 | 18228 | 10800 | -18228 |  | 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.1 Project management and compliance documentation | Lacy Pejcinovic | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 | 144.5 | 21949.55 | -21949.55 | 21097 | 3.884% | 120 | 15 | 18228 | 17520 | -40177.55 |  | 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 | 16.46% | 40 | 5 | 9480 | 7920 | -9480 |  | 2026-03-02: 25%; 2026-03-09: 25%; 2026-03-16: 25%; 2026-03-23: 25%
M2 - Sprint 1 and 2 completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M2 - Sprint 1 and 2 completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 | 17.57% | 140 | 17.5 | 29036 | 23934.4 | -29036 |  | 2026-02-23: 25%; 2026-03-02: 50%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 160 | 20 | 0 | 31680 | 0 |  | 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -24304 |  | 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M2 - Sprint 1 and 2 completion | 2.2 Build | Contingency |  |  |  | 5% | 7928.4 |  | 0 |  | 0 |  | 0 | 0 | 0 | 100% | 1 | 0.125 | 7928.4 | 0 | -7928.4 |  | 2026-03-23: 2.5%
M3 - Sprint 3 and 4 completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 152 | 19 | 31524.8 | 37240 | -31524.8 |  | 2026-03-30: 80%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 | 40.75% | 160 | 20 | 24304 | 14400 | -24304 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 | 16.46% | 80 | 10 | 18960 | 15840 | -18960 |  | 2026-03-30: 50%; 2026-04-06: 50%; 2026-04-13: 50%; 2026-04-20: 50%
M3 - Sprint 3 and 4 completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 | 3.884% | 120 | 15 | 18228 | 17520 | -18228 |  | 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 | 17.57% | 160 | 20 | 33184 | 27353.6 | -33184 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 160 | 20 | 0 | 31680 | 0 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -24304 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 | -5.991% | 80 | 10 | 12152 | 12880 | -12152 |  | 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Contingency |  |  |  | 5% | 9645.64 |  | 0 |  | 0 |  | 0 | 0 | 0 | 100% | 1 | 0.125 | 9645.64 | 0 | -9645.64 |  | 2026-04-20: 2.5%
M4 - Sprint 5 and 6 completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 160 | 20 | 33184 | 39200 | -33184 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 | 40.75% | 160 | 20 | 24304 | 14400 | -24304 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 | 16.46% | 80 | 10 | 18960 | 15840 | -18960 |  | 2026-04-27: 50%; 2026-05-04: 50%; 2026-05-11: 50%; 2026-05-18: 50%
M4 - Sprint 5 and 6 completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 | 3.884% | 160 | 20 | 24304 | 23360 | -24304 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 | 17.57% | 160 | 20 | 33184 | 27353.6 | -33184 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M4 - Sprint 5 and 6 completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -24304 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Contingency |  |  |  | 5% | 9907.082 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 1 | 0.125 | 0 | 0 | 0 |  | 2026-04-20: 2.5%
M4 - Sprint 5 and 6 completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 | -5.991% | 160 | 20 | 24304 | 25760 | -24304 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M5 - Test Completion & Go-live | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 160 | 20 | 33184 | 39200 | -33184 |  | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M5 - Test Completion & Go-live | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M5 - Test Completion & Go-live | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M5 - Test Completion & Go-live | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 | 3.884% | 80 | 10 | 12152 | 11680 | -12152 |  | 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%
M5 - Test Completion & Go-live | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M5 - Test Completion & Go-live | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M5 - Test Completion & Go-live | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M5 - Test Completion & Go-live | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 80 | 10 | 12152 | 12080 | -12152 |  | 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%
M5 - Test Completion & Go-live | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 | -5.991% | 160 | 20 | 24304 | 25760 | -24304 |  | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M6 - Hypercare completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 76 | 9.5 | 15762.4 | 18620 | -15762.4 |  | 2026-06-22: 50%; 2026-06-29: 50%; 2026-07-06: 50%; 2026-07-13: 40%
M6 - Hypercare completion | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 100%
M6 - Hypercare completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 40 | 5 | 6076 | 6040 | -6076 |  | 2026-06-22: 50%; 2026-06-29: 50%
M6 - Hypercare completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| RESOURCE LOADING | Anil Kinagi |  | Project Manager |  |  | 207.4 | [15 empty] | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 80%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 50%; 2026-06-29: 50%; 2026-07-06: 50%; 2026-07-13: 40%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Lacy Pejcinovic |  | Business Analyst |  |  | 151.9 | [15 empty] | 2026-02-09: 170%; 2026-02-16: 110%; 2026-02-23: 70%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 0%; 2026-04-06: 0%; 2026-04-13: 0%; 2026-04-20: 0%; 2026-04-27: 0%; 2026-05-04: 0%; 2026-05-11: 0%; 2026-05-18: 0%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Lynne Sutherland |  | Business Analyst |  |  | 151.9 | [15 empty] | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Hadas Yehezkel |  | ServiceNow Architect |  |  | 237 | [15 empty] | 2026-02-09: 70%; 2026-02-16: 50%; 2026-02-23: 50%; 2026-03-02: 100%; 2026-03-09: 25%; 2026-03-16: 25%; 2026-03-23: 25%; 2026-03-30: 50%; 2026-04-06: 50%; 2026-04-13: 50%; 2026-04-20: 50%; 2026-04-27: 50%; 2026-05-04: 50%; 2026-05-11: 50%; 2026-05-18: 50%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Bradley Burge |  | Lead ServiceNow Developer |  |  | 207.4 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 50%; 2026-03-02: 150%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 100%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Michelle Chant |  | Change Manager |  |  | 151.9 | [15 empty] | 2026-02-09: 20%; 2026-02-16: 30%; 2026-02-23: 85%; 2026-03-02: 20%; 2026-03-09: 0%; 2026-03-16: 0%; 2026-03-23: 0%; 2026-03-30: 0%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Phani Gollamudi |  | ServiceNow Developer |  |  | 0 | [15 empty] | 2026-02-09: 25%; 2026-02-16: 57%; 2026-02-23: 50%; 2026-03-02: 150%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 0%; 2026-05-04: 0%; 2026-05-11: 0%; 2026-05-18: 0%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Contingency |  | 0 |  |  | 1438.66 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 2.5%; 2026-02-23: 0%; 2026-03-02: 0%; 2026-03-09: 0%; 2026-03-16: 0%; 2026-03-23: 2.5%; 2026-03-30: 0%; 2026-04-06: 0%; 2026-04-13: 0%; 2026-04-20: 5%; 2026-04-27: 0%; 2026-05-04: 0%; 2026-05-11: 0%; 2026-05-18: 0%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Mahesh Vemegal |  | Lead ServiceNow Developer |  |  | 207.4 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 25%; 2026-03-02: 50%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Kosta Walker-Laskos |  | ServiceNow Developer |  |  | 151.9 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 0%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%; 2026-06-22: 50%; 2026-06-29: 50%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Contractor-Tester-Manager |  | Senior Tester |  |  | 151.9 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 0%; 2026-03-02: 0%; 2026-03-09: 0%; 2026-03-16: 0%; 2026-03-23: 0%; 2026-03-30: 0%; 2026-04-06: 0%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%

## Time Plan (Single Release)
Forecast Date | 2026-03-02 | 887523.63 | 827429.6 | -887528.89 |  |  | 907273.5 | [8 empty] | -6.3% | [6 empty] | Monday Commencing (Select) | [32 empty] | Hypercare
Contract Start Date | 2026-02-09 | -6.3% | [7 empty] | Delivery | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492 | 493 | 494 | 495 | 496 | 497 | 498 | 499 | 500 | 501 | 502 | 503 | 504 | 505 | 506 | 507 | 508 | 509 | 510 | 511 | 512 | 513 | 514 | 515 | 516 | 517 | 518 | 519 | 520 | 521 | 522 | 523 | 524 | 525 | 526 | 527 | 528 | 529 | 530 | 531 | 532 | 533 | 534 | 535 | 536 | 537 | 538 | 539 | 540 | 541 | 542 | 543 | 544 | 545 | 546 | 547 | 548 | 549 | 550 | 551 | 552 | 553 | 554 | 555 | 556 | 557 | 558 | 559 | 560 | 561 | 562 | 563 | 564 | 565 | 566 | 567 | 568 | 569 | 570 | 571 | 572 | 573 | 574 | 575 | 576 | 577 | 578 | 579 | 580 | 581 | 582 | 583 | 584 | 585 | 586 | 587 | 588 | 589 | 590 | 591
Milestone | Deliverable | Resource | Charge Out Level | Job Role | Panel Hourly Rate $ ex-GST | Discount (%) | Discounted Hourly Rate $ ex GST | Discounted Daily Rate $ ex-GST | Hourly Gross Cost $ | Budget Hours | Budget $ ex GST | Actual Hours as at 09-Feb | Charge $ ex GST | Balance $ ex GST (Budget - Charge) | Gross Cost $ ex GST | Gross Margin | Forecast hours | Forecast Days | Forecast $ ex GST | Forecast Gross Cost $ ex GST | Variance at completion (ex GST) | Variance at completion (%) | time axis 2026-02-09 to 2037-06-01
| Account Manager | Aleksandar Vranesevic | Panel | Digital Marketplace 2 | [18 empty] | 2026-03-09: 20%; 2026-03-30: 20%; 2026-04-06: 20%; 2026-04-20: 20%; 2026-06-01: 20%; 2026-06-08: 20%; 2026-10-05: 20%; 2026-12-21: 100%; 2026-12-28: 100%; 2027-01-25: 20%; 2027-03-08: 20%; 2027-03-22: 20%; 2027-03-29: 20%; 2027-04-26: 20%; 2027-05-31: 20%; 2027-06-14: 20%; 2027-10-04: 20%; 2027-12-20: 100%; 2027-12-27: 100%; 2028-01-24: 20%; 2028-03-13: 40%; 2028-03-20: 20%; 2028-04-24: 20%; 2028-05-29: 20%; 2028-06-12: 20%; 2028-10-02: 20%; 2028-12-25: 100%; 2029-01-01: 100%; 2029-01-22: 20%; 2029-03-12: 20%; 2029-03-26: 20%; 2029-04-02: 20%; 2029-04-23: 20%; 2029-05-28: 20%; 2029-06-11: 20%
| Engagement Manager | Hadas Yehezkel | Category | Market Rates - Solutions implementation services | [5 empty] | 0 | 0 | 716.25 | 112758.45 | -112758.45 | 116011.5 | -6.3% | 4889 | 611.125 | 774770.44 | 827429.6 | -887528.89
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 | 120 | 24888 | -24888 | 29400 | -18.13% | 20 | 2.5 | 4148 | 4900 | -29036 |  | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 50%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Lacy Pejcinovic | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 | 144.5 | 21949.55 | -21949.55 | 21097 | 3.884% | 40 | 5 | 6076 | 5840 | -28025.55 |  | 2026-02-09: 170%; 2026-02-16: 110%; 2026-02-23: 70%; 2026-03-02: 100%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 | 120 | 18228 | -18228 | 10800 | 40.75% | 40 | 5 | 6076 | 3600 | -24304 |  | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 | 66 | 15642 | -15642 | 13068 | 16.46% | 30 | 3.75 | 7110 | 5940 | -22752 |  | 2026-02-09: 70%; 2026-02-16: 50%; 2026-02-23: 50%; 2026-03-02: 75%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Bradley Burge | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 151 |  | 0 |  | 0 | 0 | 0 | 27.19% | 20 | 2.5 | 4148 | 3020 | -4148 |  | 2026-02-23: 50%; 2026-03-02: 50%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 | 66.5 | 10101.35 | -10101.35 | 9709 | 3.884% | 8 | 1 | 1215.2 | 1168 | -11316.55 |  | 2026-02-09: 20%; 2026-02-16: 30%; 2026-02-23: 85%; 2026-03-02: 20%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 | 54.75 | 0 | 0 | 10840.5 | 100% | 20 | 2.5 | 0 | 3960 | 0 |  | 2026-02-09: 25%; 2026-02-16: 57%; 2026-02-23: 50%; 2026-03-02: 50%
M1 - Discovery Completion | 1.3 Detailed delivery plan, RACI of build/delivery meeting AGD Operating Model requirements | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M1 - Discovery Completion | 1.4 Acceptance certificate | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Contingency |  |  |  | 5% | 1438.66 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 2026-02-16: 2.5%
M2 - Sprint 1 and 2 completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 140 | 17.5 | 29036 | 34300 | -29036 |  | 2026-03-02: 50%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 | 40.75% | 120 | 15 | 18228 | 10800 | -18228 |  | 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.1 Project management and compliance documentation | Lacy Pejcinovic | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 | 144.5 | 21949.55 | -21949.55 | 21097 | 3.884% | 120 | 15 | 18228 | 17520 | -40177.55 |  | 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 | 16.46% | 40 | 5 | 9480 | 7920 | -9480 |  | 2026-03-02: 25%; 2026-03-09: 25%; 2026-03-16: 25%; 2026-03-23: 25%
M2 - Sprint 1 and 2 completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M2 - Sprint 1 and 2 completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 | 17.57% | 140 | 17.5 | 29036 | 23934.4 | -29036 |  | 2026-02-23: 25%; 2026-03-02: 50%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 160 | 20 | 0 | 31680 | 0 |  | 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -24304 |  | 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M2 - Sprint 1 and 2 completion | 2.2 Build | Contingency |  |  |  | 5% | 7928.4 |  | 0 |  | 0 |  | 0 | 0 | 0 | 100% | 1 | 0.125 | 7928.4 | 0 | -7928.4 |  | 2026-03-23: 2.5%
M3 - Sprint 3 and 4 completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 152 | 19 | 31524.8 | 37240 | -31524.8 |  | 2026-03-30: 80%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 | 40.75% | 160 | 20 | 24304 | 14400 | -24304 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 | 16.46% | 80 | 10 | 18960 | 15840 | -18960 |  | 2026-03-30: 50%; 2026-04-06: 50%; 2026-04-13: 50%; 2026-04-20: 50%
M3 - Sprint 3 and 4 completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 | 3.884% | 120 | 15 | 18228 | 17520 | -18228 |  | 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 | 17.57% | 160 | 20 | 33184 | 27353.6 | -33184 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 160 | 20 | 0 | 31680 | 0 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -24304 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 | -5.991% | 80 | 10 | 12152 | 12880 | -12152 |  | 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Contingency |  |  |  | 5% | 9645.64 |  | 0 |  | 0 |  | 0 | 0 | 0 | 100% | 1 | 0.125 | 9645.64 | 0 | -9645.64 |  | 2026-04-20: 2.5%
M4 - Sprint 5 and 6 completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 160 | 20 | 33184 | 39200 | -33184 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 | 40.75% | 160 | 20 | 24304 | 14400 | -24304 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 | 16.46% | 80 | 10 | 18960 | 15840 | -18960 |  | 2026-04-27: 50%; 2026-05-04: 50%; 2026-05-11: 50%; 2026-05-18: 50%
M4 - Sprint 5 and 6 completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 | 3.884% | 160 | 20 | 24304 | 23360 | -24304 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 | 17.57% | 160 | 20 | 33184 | 27353.6 | -33184 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 160 | 20 | 0 | 31680 | 0 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -24304 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M3 - Sprint 3 and 4 completion | 2.2 Build | Contingency |  |  |  | 5% | 9907.082 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 1 | 0.125 | 0 | 0 | 0 |  | 2026-04-20: 2.5%
M4 - Sprint 5 and 6 completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 | -5.991% | 160 | 20 | 24304 | 25760 | -24304 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M5 - Test Completion & Go-live | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 160 | 20 | 33184 | 39200 | -33184 |  | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M5 - Test Completion & Go-live | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M5 - Test Completion & Go-live | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M5 - Test Completion & Go-live | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 | 3.884% | 80 | 10 | 12152 | 11680 | -12152 |  | 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%
M5 - Test Completion & Go-live | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M5 - Test Completion & Go-live | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M5 - Test Completion & Go-live | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 120 | 15 | 0 | 23760 | 0 |  | 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 100%; 2026-06-15: 100%
M5 - Test Completion & Go-live | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 80 | 10 | 12152 | 12080 | -12152 |  | 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%
M5 - Test Completion & Go-live | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 | -5.991% | 160 | 20 | 24304 | 25760 | -24304 |  | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M6 - Hypercare completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 |  | 0 |  | 0 | 0 | 0 | -18.13% | 76 | 9.5 | 15762.4 | 18620 | -15762.4 |  | 2026-06-22: 50%; 2026-06-29: 50%; 2026-07-06: 50%; 2026-07-13: 40%
M6 - Hypercare completion | 2.1 Project management and compliance documentation | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 |  | 0 |  | 0 | 0 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | -30256 |  | 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 100%
M6 - Hypercare completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 198 |  | 0 |  | 0 | 0 | 0 |  | 40 | 5 | 0 | 7920 | 0 |  | 2026-06-22: 50%; 2026-06-29: 50%
M6 - Hypercare completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 |  | 0 |  | 0 | 0 | 0 | 0.5925% | 40 | 5 | 6076 | 6040 | -6076 |  | 2026-06-22: 50%; 2026-06-29: 50%
M6 - Hypercare completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| RESOURCE LOADING | Anil Kinagi |  | Project Manager |  |  | 207.4 | [15 empty] | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 80%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 50%; 2026-06-29: 50%; 2026-07-06: 50%; 2026-07-13: 40%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Lacy Pejcinovic |  | Business Analyst |  |  | 151.9 | [15 empty] | 2026-02-09: 170%; 2026-02-16: 110%; 2026-02-23: 70%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 0%; 2026-04-06: 0%; 2026-04-13: 0%; 2026-04-20: 0%; 2026-04-27: 0%; 2026-05-04: 0%; 2026-05-11: 0%; 2026-05-18: 0%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Lynne Sutherland |  | Business Analyst |  |  | 151.9 | [15 empty] | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Hadas Yehezkel |  | ServiceNow Architect |  |  | 237 | [15 empty] | 2026-02-09: 70%; 2026-02-16: 50%; 2026-02-23: 50%; 2026-03-02: 100%; 2026-03-09: 25%; 2026-03-16: 25%; 2026-03-23: 25%; 2026-03-30: 50%; 2026-04-06: 50%; 2026-04-13: 50%; 2026-04-20: 50%; 2026-04-27: 50%; 2026-05-04: 50%; 2026-05-11: 50%; 2026-05-18: 50%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Bradley Burge |  | Lead ServiceNow Developer |  |  | 207.4 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 50%; 2026-03-02: 150%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 100%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Michelle Chant |  | Change Manager |  |  | 151.9 | [15 empty] | 2026-02-09: 20%; 2026-02-16: 30%; 2026-02-23: 85%; 2026-03-02: 20%; 2026-03-09: 0%; 2026-03-16: 0%; 2026-03-23: 0%; 2026-03-30: 0%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Phani Gollamudi |  | ServiceNow Developer |  |  | 0 | [15 empty] | 2026-02-09: 25%; 2026-02-16: 57%; 2026-02-23: 50%; 2026-03-02: 150%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 50%; 2026-06-29: 50%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Contingency |  | 0 |  |  | 1438.66 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 2.5%; 2026-02-23: 0%; 2026-03-02: 0%; 2026-03-09: 0%; 2026-03-16: 0%; 2026-03-23: 2.5%; 2026-03-30: 0%; 2026-04-06: 0%; 2026-04-13: 0%; 2026-04-20: 5%; 2026-04-27: 0%; 2026-05-04: 0%; 2026-05-11: 0%; 2026-05-18: 0%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Mahesh Vemegal |  | Lead ServiceNow Developer |  |  | 207.4 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 25%; 2026-03-02: 50%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Kosta Walker-Laskos |  | ServiceNow Developer |  |  | 151.9 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 0%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%; 2026-06-22: 50%; 2026-06-29: 50%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Contractor-Tester-Manager |  | Senior Tester |  |  | 151.9 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 0%; 2026-03-02: 0%; 2026-03-09: 0%; 2026-03-16: 0%; 2026-03-23: 0%; 2026-03-30: 0%; 2026-04-06: 0%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%

## Milestones
Milestone | deliverable | start 3 NOV 2025 | end 12 motnhs
M1 Discovery | 1.1 Detailed requirements, business process mapping complete and signed off
M1 Discovery | 1.2 License costs
M1 Discovery | 1.3 Detailed delivery plan and RACI of build and delivery meeting AGD Operating Model requirements
M1 Discovery | 1.4 Acceptance certificate | 2025-12-03 | 4 weeks
M2A Build and delivery | 2.0 Supply of required software licenses to cover year 1, including support and maintenance |  | To be specified by vendor at phase 1 | (Conditional of satisfactory discovery sign off)
M2A Build and delivery | 2.1 Project management/compliance
M2A Build and delivery | 2.2 Build
M2A Build and delivery | 2.3 Testing: including testing plan and UAT requirements
M2A Build and delivery | 2.4 Data migration
M2A Build and delivery | 2.5 Business Continuity and user guides
M2A Build and delivery | 2.6 Acceptance certificate
M2A Build and delivery | 2.7 Go Live | 2026-06-15
M2A Build and delivery | 2.8 Hypercare | 2026-07-15 | Minimum 4 weeks
M2A Build and delivery | 2.9 Handover |  | To be specified by vendor at phase 1
M2B AI Proof of Concept | 2.10 Detailed requirements, business process mapping complete and signed off | 2025-12-03 | Parallel to phase 1
M2B AI Proof of Concept | 2.11 Integration into relevant project and guidance documents |  | Desirable to be parallel to phase 2A
M2B AI Proof of Concept | 2.12 Proof of Concept - including the delivery of an accuracy, return on investment, delivery plan to production and model upgrade plan |  | Desirable to be parallel to phase 2A
M2B AI Proof of Concept | 2.13 Detailed evaluation report and delivery plan |  | Desirable to be parallel to phase 2A
M2B AI Proof of Concept | 2.14 Acceptance certificate | 2026-07-15 | (parallel to phase 1 and 2A)
M2C Self-service portal | 2.15 Detailed requirements, business process mapping complete and signed off | 2025-12-03 | Parallel to phase 1
M2C Self-service portal | 2.16 Integration into relevant project and guidance documents
M2C Self-service portal | 2.17 Build/delivery of self-service portal
M2C Self-service portal | 2.18 Acceptance certificate | 2026-07-15 | Desirable to be parallel to phase 2A
M3 Implementation of AI | 3.1 Integration into relevant project and guidance documents | 2026-07-15 | As per 2B: AI Proof of Concept delivery plan
M3 Implementation of AI | 3.2 Implementation and release of the AI capability in POC into Production | 2026-07-15
M3 Implementation of AI | 3.3 Completion of Commonwealth responsible AI use and relevant assessments, IRAP assessment (if applicable) and Privacy Impact Assessment (PIA) | 2026-07-15

## Time Plan (Lacy)) (hidden)
Forecast Date | 2026-02-09 | [5 empty] | 907273.5 | [8 empty] | 14.47% |  |  |  | 887441.184 |  |  | Monday Commencing (Select) | [32 empty] | Hypercare
Contract Start Date | 2026-02-09 | [8 empty] | Delivery | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492 | 493 | 494 | 495 | 496 | 497 | 498 | 499 | 500 | 501 | 502 | 503 | 504 | 505 | 506 | 507 | 508 | 509 | 510 | 511 | 512 | 513 | 514 | 515 | 516 | 517 | 518 | 519 | 520 | 521 | 522 | 523 | 524 | 525 | 526 | 527 | 528 | 529 | 530 | 531 | 532 | 533 | 534 | 535 | 536 | 537 | 538 | 539 | 540 | 541 | 542 | 543 | 544 | 545 | 546 | 547 | 548 | 549 | 550 | 551 | 552 | 553 | 554 | 555 | 556 | 557 | 558 | 559 | 560 | 561 | 562 | 563 | 564 | 565 | 566 | 567 | 568 | 569 | 570 | 571 | 572 | 573 | 574 | 575 | 576 | 577 | 578 | 579 | 580 | 581 | 582 | 583 | 584 | 585 | 586 | 587 | 588 | 589 | 590 | 591
Milestone | Deliverable | Resource | Charge Out Level | Job Role | Panel Hourly Rate $ ex-GST | Discount (%) | Discounted Hourly Rate $ ex GST | Discounted Daily Rate $ ex-GST | Hourly Gross Cost $ | Budget Hours | Budget $ ex GST | Actual Hours as at 09-Feb | Charge $ ex GST | Balance $ ex GST (Budget - Charge) | Gross Cost $ ex GST | Gross Margin | Forecast hours | Forecast Days | Forecast $ ex GST | Forecast Gross Cost $ ex GST | Variance at completion (ex GST) | Variance at completion (%) | time axis 2026-02-09 to 2037-06-01
| Account Manager | Aleksandar Vranesevic | Panel | Digital Marketplace 2 | [18 empty] | 2026-03-09: 20%; 2026-03-30: 20%; 2026-04-06: 20%; 2026-04-20: 20%; 2026-06-01: 20%; 2026-06-08: 20%; 2026-10-05: 20%; 2026-12-21: 100%; 2026-12-28: 100%; 2027-01-25: 20%; 2027-03-08: 20%; 2027-03-22: 20%; 2027-03-29: 20%; 2027-04-26: 20%; 2027-05-31: 20%; 2027-06-14: 20%; 2027-10-04: 20%; 2027-12-20: 100%; 2027-12-27: 100%; 2028-01-24: 20%; 2028-03-13: 40%; 2028-03-20: 20%; 2028-04-24: 20%; 2028-05-29: 20%; 2028-06-12: 20%; 2028-10-02: 20%; 2028-12-25: 100%; 2029-01-01: 100%; 2029-01-22: 20%; 2029-03-12: 20%; 2029-03-26: 20%; 2029-04-02: 20%; 2029-04-23: 20%; 2029-05-28: 20%; 2029-06-11: 20%
| Engagement Manager | Hadas Yehezkel | Category | Market Rates - Solutions implementation services | [5 empty] | 12397 | 2161217.256 | 0 | 0 | 2161217.256 | 0 | 14.47% | 5178.4 | 647.3 | 887441.184 | 759058.4 | 1013539.04 | 46.9%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 | 120 | 24888 |  | 0 | 24888 | 0 | -18.13% | 140 | 17.5 | 29036 | 34300 | -4148 | -16.67% | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 50%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Lacy Pejcinovic | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 146 | 160 | 24304 |  | 0 | 24304 | 0 | 3.884% | 160 | 20 | 24304 | 23360 | 0 | 0% | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Lynne Sutherland | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 90 | 160 | 24304 |  | 0 | 24304 | 0 | 40.75% | 160 | 20 | 24304 | 14400 | 0 | 0% | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 | 100 | 23700 |  | 0 | 23700 | 0 | 16.46% | 160 | 20 | 37920 | 31680 | -14220 | -60% | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Bradley Burge | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 151 | 90 | 18666 |  | 0 | 18666 | 0 | 27.19% | 40 | 5 | 8296 | 6040 | 10370 | 55.56% | 2026-02-23: 50%; 2026-03-02: 50%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 | 232 | 35240.8 |  | 0 | 35240.8 | 0 | 3.884% | 32 | 4 | 4860.8 | 4672 | 30380 | 86.21% | 2026-02-09: 20%; 2026-02-16: 20%; 2026-02-23: 20%; 2026-03-02: 20%
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Phani Gollamudi | Level 4 | Lead ServiceNow Developer | 305 | 100% | 0 | 0 | 0 | 90 | 0 |  | 0 | 0 | 0 | 100% | 60 | 7.5 | 0 | 0 | 0 |  | 2026-02-16: 50%; 2026-02-23: 50%; 2026-03-02: 50%
M1 - Discovery Completion | 1.3 Detailed delivery plan, RACI of build/delivery meeting AGD Operating Model requirements | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 | 32 | 6636.8 |  | 0 | 6636.8 | 0 |  | 0 | 0 | 0 | 0 | 6636.8 | 100%
M1 - Discovery Completion | 1.4 Acceptance certificate | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
M1 - Discovery Completion | 1.1 Detailed requirements, business process mapping | Contingency |  |  |  | 5% | 6436.04 |  | 0 | 1 | 6436.04 |  | 0 | 6436.04 | 0 | 100% | 4 | 0.5 | 25744.16 | 0 |  |  | 2026-02-16: 10%
M2 - Sprint 1 and 2 completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 | 280 | 58072 |  | 0 | 58072 | 0 | -18.13% | 140 | 17.5 | 29036 | 34300 |  |  | 2026-03-02: 50%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.1 Project management and compliance documentation | Lacy Pejcinovic | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 146 | 270 | 41013 |  | 0 | 41013 | 0 | 3.884% | 120 | 15 | 18228 | 17520 |  |  | 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 50%; 2026-03-23: 50%
M2 - Sprint 1 and 2 completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 | 140 | 33180 |  | 0 | 33180 | 0 | 16.46% | 40 | 5 | 9480 | 7920 | 23700 | 71.43% | 2026-03-02: 25%; 2026-03-09: 25%; 2026-03-16: 25%; 2026-03-23: 25%
M2 - Sprint 1 and 2 completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 | 232 | 35240.8 |  | 0 | 35240.8 | 0 | 3.884% | 3.2 | 0.4 | 486.08 | 467.2 | 34754.72 | 98.62% | bar: 2026-03-02
M2 - Sprint 1 and 2 completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 | 380 | 78812 |  | 0 | 78812 | 0 | 17.57% | 80 | 10 | 16592 | 13676.8 | 62220 | 78.95% | 2026-03-02: 50%; 2026-03-09: 50%; 2026-03-16: 50%; 2026-03-23: 50%
M2 - Sprint 1 and 2 completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 | 520 | 98332 |  | 0 | 98332 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | 68076 | 69.23% | 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 0 | 120 | 0 |  | 0 | 0 | 0 |  | 160 | 20 | 0 | 0 | 0 |  | 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 | 120 | 18228 |  | 0 | 18228 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -6076 | -33.33% | 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%
M2 - Sprint 1 and 2 completion | 2.2 Build | Contingency |  |  |  | 5% | 7706.312 |  | 0 | 1 | 7706.312 |  | 0 | 7706.312 | 0 | 100% | 4 | 0.5 | 30825.248 | 0 |  |  | 2026-03-23: 10%
M2 - Sprint 1 and 2 completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 | 220 | 33418 |  | 0 | 33418 | 0 |  | 0 | 0 | 0 | 0 | 33418 | 100%
M3 - Sprint 2 and 3 completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 | 280 | 58072 |  | 0 | 58072 | 0 | -18.13% | 140 | 17.5 | 29036 | 34300 |  |  | 2026-03-30: 50%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 2 and 3 completion | 2.1 Project management and compliance documentation | Lacy Pejcinovic | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 146 | 270 | 41013 |  | 0 | 41013 | 0 | 3.884% | 80 | 10 | 12152 | 11680 |  |  | 2026-03-30: 50%; 2026-04-06: 50%; 2026-04-13: 50%; 2026-04-20: 50%
M3 - Sprint 2 and 3 completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 | 140 | 33180 |  | 0 | 33180 | 0 | 16.46% | 40 | 5 | 9480 | 7920 | 23700 | 71.43% | 2026-03-30: 25%; 2026-04-06: 25%; 2026-04-13: 25%; 2026-04-20: 25%
M3 - Sprint 2 and 3 completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 | 232 | 35240.8 |  | 0 | 35240.8 | 0 | 3.884% | 123.2 | 15.4 | 18714.08 | 17987.2 | 16526.72 | 46.9% | 2026-03-30: 8%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 2 and 3 completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 | 380 | 78812 |  | 0 | 78812 | 0 | 17.57% | 160 | 20 | 33184 | 27353.6 | 45628 | 57.89% | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 2 and 3 completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 | 520 | 98332 |  | 0 | 98332 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | 68076 | 69.23% | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 2 and 3 completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 0 | 120 | 0 |  | 0 | 0 | 0 |  | 160 | 20 | 0 | 0 | 0 |  | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 2 and 3 completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 | 120 | 18228 |  | 0 | 18228 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -6076 | -33.33% | 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%
M3 - Sprint 2 and 3 completion | 2.2 Build | Contingency |  |  |  | 5% | 7856.304 |  | 0 | 1 | 7856.304 |  | 0 | 7856.304 | 0 | 100% | 4 | 0.5 | 31425.216 | 0 |  |  | 2026-04-20: 10%
M3 - Sprint 2 and 3 completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 | 220 | 33418 |  | 0 | 33418 | 0 | -5.991% | 80 | 10 | 12152 | 12880 | 21266 | 63.64% | 2026-04-13: 100%; 2026-04-20: 100%
M4 - Sprint 5 and 6 completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 | 280 | 58072 |  | 0 | 58072 | 0 | -18.13% | 160 | 20 | 33184 | 39200 |  |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.1 Project management and compliance documentation | Lacy Pejcinovic | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 146 | 270 | 41013 |  | 0 | 41013 | 0 | 3.884% | 40 | 5 | 6076 | 5840 |  |  | 2026-04-27: 25%; 2026-05-04: 25%; 2026-05-11: 25%; 2026-05-18: 25%
M4 - Sprint 5 and 6 completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 | 140 | 33180 |  | 0 | 33180 | 0 | 16.46% | 40 | 5 | 9480 | 7920 | 23700 | 71.43% | 2026-04-27: 25%; 2026-05-04: 25%; 2026-05-11: 25%; 2026-05-18: 25%
M4 - Sprint 5 and 6 completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 | 232 | 35240.8 |  | 0 | 35240.8 | 0 | 3.884% | 160 | 20 | 24304 | 23360 | 10936.8 | 31.03% | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 | 380 | 78812 |  | 0 | 78812 | 0 | 17.57% | 160 | 20 | 33184 | 27353.6 | 45628 | 57.89% | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 | 520 | 98332 |  | 0 | 98332 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | 68076 | 69.23% | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 0 | 120 | 0 |  | 0 | 0 | 0 |  | 160 | 20 | 0 | 0 | 0 |  | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 | 120 | 18228 |  | 0 | 18228 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -6076 | -33.33% | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M4 - Sprint 5 and 6 completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 | 220 | 33418 |  | 0 | 33418 | 0 | -5.991% | 160 | 20 | 24304 | 25760 | 9114 | 27.27% | 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%
M5 - Test Completion & Go-live | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 | 280 | 58072 |  | 0 | 58072 | 0 | -18.13% | 160 | 20 | 33184 | 39200 |  |  | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M5 - Test Completion & Go-live | 2.1 Project management and compliance documentation | Lacy Pejcinovic | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 146 | 270 | 41013 |  | 0 | 41013 | 0 |  | 0 | 0 | 0 | 0
M5 - Test Completion & Go-live | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 | 140 | 33180 |  | 0 | 33180 | 0 |  | 0 | 0 | 0 | 0 | 33180 | 100%
M5 - Test Completion & Go-live | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 | 232 | 35240.8 |  | 0 | 35240.8 | 0 | 3.884% | 80 | 10 | 12152 | 11680 | 23088.8 | 65.52% | 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%
M5 - Test Completion & Go-live | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 | 380 | 78812 |  | 0 | 78812 | 0 |  | 0 | 0 | 0 | 0 | 78812 | 100%
M5 - Test Completion & Go-live | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 | 520 | 98332 |  | 0 | 98332 | 0 | 20.15% | 160 | 20 | 30256 | 24160 | 68076 | 69.23% | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M5 - Test Completion & Go-live | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 0 | 120 | 0 |  | 0 | 0 | 0 |  | 160 | 20 | 0 | 0 | 0 |  | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M5 - Test Completion & Go-live | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 | 120 | 18228 |  | 0 | 18228 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -6076 | -33.33% | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M5 - Test Completion & Go-live | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 | 220 | 33418 |  | 0 | 33418 | 0 | -5.991% | 160 | 20 | 24304 | 25760 | 9114 | 27.27% | 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%
M6 - Hypercare completion | 2.1 Project management and compliance documentation | Anil Kinagi | Level 4 | Project Manager | 305 | 32% | 207.4 | 1659.2 | 245 | 280 | 58072 |  | 0 | 58072 | 0 | -18.13% | 40 | 5 | 8296 | 9800 |  |  | 2026-06-22: 25%; 2026-06-29: 25%; 2026-07-06: 25%; 2026-07-13: 25%
M6 - Hypercare completion | 2.1 Project management and compliance documentation | Lacy Pejcinovic | Level 3 | Business Analyst | 245 | 38% | 151.9 | 1215.2 | 146 | 270 | 41013 |  | 0 | 41013 | 0 |  | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Hadas Yehezkel | Level 5 | ServiceNow Architect | 395 | 40% | 237 | 1896 | 198 | 140 | 33180 |  | 0 | 33180 | 0 |  | 0 | 0 | 0 | 0 | 33180 | 100%
M6 - Hypercare completion | 2.2 Build | Michelle Chant | Level 3 | Change Manager | 245 | 38% | 151.9 | 1215.2 | 146 | 232 | 35240.8 |  | 0 | 35240.8 | 0 | 3.884% | 16 | 2 | 2430.4 | 2336 | 32810.4 | 93.1% | 2026-06-22: 20%; 2026-06-29: 20%
M6 - Hypercare completion | 2.2 Build | Mahesh Vemegal | Level 4 | Lead ServiceNow Developer | 305 | 32% | 207.4 | 1659.2 | 170.96 | 380 | 78812 |  | 0 | 78812 | 0 |  | 0 | 0 | 0 | 0 | 78812 | 100%
M6 - Hypercare completion | 2.2 Build | Bradley Burge | Level 4 | ServiceNow Developer | 305 | 38% | 189.1 | 1512.8 | 151 | 520 | 98332 |  | 0 | 98332 | 0 | 20.15% | 152 | 19 | 28743.2 | 22952 | 69588.8 | 70.77% | 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 80%
M6 - Hypercare completion | 2.2 Build | Phani Gollamudi | Level 3 | ServiceNow Developer | 245 | 100% | 0 | 0 | 0 | 120 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
M6 - Hypercare completion | 2.2 Build | Kosta Walker-Laskos | Level 3 | ServiceNow Developer | 245 | 38% | 151.9 | 1215.2 | 151 | 120 | 18228 |  | 0 | 18228 | 0 | 0.5925% | 160 | 20 | 24304 | 24160 | -6076 | -33.33% | 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 100%
M6 - Hypercare completion | 2.2 Build | Contractor-Tester-Manager | Level 3 | Senior Tester | 245 | 38% | 151.9 | 1215.2 | 161 | 220 | 33418 |  | 0 | 33418 | 0 |  | 0 | 0 | 0 | 0 | 33418 | 100%
| RESOURCE LOADING | Anil Kinagi |  | Project Manager |  |  | 207.4 | [15 empty] | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 50%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 25%; 2026-06-29: 25%; 2026-07-06: 25%; 2026-07-13: 25%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Lacy Pejcinovic |  | Business Analyst |  |  | 151.9 | [15 empty] | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 200%; 2026-03-09: 100%; 2026-03-16: 50%; 2026-03-23: 50%; 2026-03-30: 50%; 2026-04-06: 50%; 2026-04-13: 50%; 2026-04-20: 50%; 2026-04-27: 25%; 2026-05-04: 25%; 2026-05-11: 25%; 2026-05-18: 25%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Lynne Sutherland |  | #N/A |  |  | 151.9 | [15 empty] | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 100%; 2026-03-09: 0%; 2026-03-16: 0%; 2026-03-23: 0%; 2026-03-30: 0%; 2026-04-06: 0%; 2026-04-13: 0%; 2026-04-20: 0%; 2026-04-27: 0%; 2026-05-04: 0%; 2026-05-11: 0%; 2026-05-18: 0%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Hadas Yehezkel |  | ServiceNow Architect |  |  | 237 | [15 empty] | 2026-02-09: 100%; 2026-02-16: 100%; 2026-02-23: 100%; 2026-03-02: 125%; 2026-03-09: 25%; 2026-03-16: 25%; 2026-03-23: 25%; 2026-03-30: 25%; 2026-04-06: 25%; 2026-04-13: 25%; 2026-04-20: 25%; 2026-04-27: 25%; 2026-05-04: 25%; 2026-05-11: 25%; 2026-05-18: 25%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Bradley Burge |  | ServiceNow Developer |  |  | 1152.9 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 50%; 2026-03-02: 150%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 80%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Michelle Chant |  | Change Manager |  |  | 151.9 | [15 empty] | 2026-02-09: 20%; 2026-02-16: 20%; 2026-02-23: 20%; 2026-03-02: 28%; 2026-03-09: 0%; 2026-03-16: 0%; 2026-03-23: 0%; 2026-03-30: 8%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 50%; 2026-06-01: 50%; 2026-06-08: 50%; 2026-06-15: 50%; 2026-06-22: 20%; 2026-06-29: 20%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Phani Gollamudi |  | ServiceNow Developer |  |  | 0 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 50%; 2026-02-23: 50%; 2026-03-02: 150%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Contingency |  | 0 |  |  | 6436.04 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 10%; 2026-02-23: 0%; 2026-03-02: 0%; 2026-03-09: 0%; 2026-03-16: 0%; 2026-03-23: 10%; 2026-03-30: 0%; 2026-04-06: 0%; 2026-04-13: 0%; 2026-04-20: 10%; 2026-04-27: 0%; 2026-05-04: 0%; 2026-05-11: 0%; 2026-05-18: 0%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Mahesh Vemegal |  | Tester Manager |  |  | 207.4 | [15 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 0%; 2026-03-02: 50%; 2026-03-09: 50%; 2026-03-16: 50%; 2026-03-23: 50%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 0%; 2026-06-01: 0%; 2026-06-08: 0%; 2026-06-15: 0%; 2026-06-22: 0%; 2026-06-29: 0%; 2026-07-06: 0%; 2026-07-13: 0%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
|  | Kosta Walker-Laskos | [20 empty] | 2026-02-09: 0%; 2026-02-16: 0%; 2026-02-23: 0%; 2026-03-02: 100%; 2026-03-09: 100%; 2026-03-16: 100%; 2026-03-23: 100%; 2026-03-30: 100%; 2026-04-06: 100%; 2026-04-13: 100%; 2026-04-20: 100%; 2026-04-27: 100%; 2026-05-04: 100%; 2026-05-11: 100%; 2026-05-18: 100%; 2026-05-25: 100%; 2026-06-01: 100%; 2026-06-08: 100%; 2026-06-15: 100%; 2026-06-22: 100%; 2026-06-29: 100%; 2026-07-06: 100%; 2026-07-13: 100%; 2026-07-20: 0%; 2026-07-27: 0%; 2026-08-03: 0%; 2026-08-10: 0%; 2026-08-17: 0%; 2026-08-24: 0%; 2026-08-31: 0%; 2026-09-07: 0%; 2026-09-14: 0%; 2026-09-21: 0%; 2026-09-28: 0%; 2026-10-05: 0%; 2026-10-12: 0%; 2026-10-19: 0%; 2026-10-26: 0%; 2026-11-02: 0%; 2026-11-09: 0%; 2026-11-16: 0%; 2026-11-23: 0%; 2026-11-30: 0%; 2026-12-07: 0%; 2026-12-14: 0%; 2026-12-21: 0%; 2026-12-28: 0%
Contractor-Tester-Manager

## Sheet1
# | Milestone Title | Acceptance Criteria | Amount
M1 | Discovery Completion | 1. Delivery of Detailed Delivery plan 2. Test Strategy 3. Change Management Plan Training Strategy 4. High-level Solution Design 5. Business Requirements and Process Maps | 78726.48 | M1 - Discovery Completion
M2 | Sprint 1 and 2 completion | 1. Data Migration Plan 2. Acceptance of Sprint 1 and 2 user stories 3. System Information Management Plan 4. Test Plan 5. Privacy Impact Assessment | 221880.9075 | M2 - Sprint 1 and 2 completion
M3 | Sprint 2 and 3 completion | 1. System Risk Assessment Plan 2. Acceptance of Sprint 3 and 4 user stories 3. Business Continuity Plan 4. AI Evaluation Report | 221880.9075 | M3 - Sprint 2 and 3 completion
M4 | Sprint 5 and 6 completion | 1. As-built documentation 2. Acceptance of Sprint 5 and 6 user stories 3. Authority to Operate - Application | 177504.726 | M4 - Sprint 5 and 6 completion
M5 | Test Completion & Go-live | 1. SIT Test Closure Report 2. Test Progress reports 3. UAT Test Closure 4. Deployment Plan | 97627.5993 | M5 - Test Completion & Go-live
M6 | Hypercare completion | 1. Standard Operating Procedures (SOPs) 2. Training instructions reviewed and approved 3. Disaster Recovery Plan – Application System | 89903.01 | M6 - Hypercare completion
887523.63
42263
4.762%